The Schedule Forensics

Prompt Engineering

Reference Guide

Edition 1.3  •  Tool Revision 2 Build Directive

Updated Plan — Recap

Greenfield rebuild  •  Multi-agent orchestration  •  CUI-local

Prepared for: Papisito

AI-Schedule-Analysis-Solutions  •  polittdj

April 2026

# Revision History

This document is reissued whenever the build plan drifts from what was committed in a prior edition. Each row records what changed and why, so you can load the latest edition into a chat session and catch any drift Claude may have accumulated.

| Edition | Date | Changes |
| --- | --- | --- |
| 1.0 | April 16, 2026 | Initial issue. Four-section structure (0, A, B, C) plus recipes and cheat sheet. Built on the assumption of a clean repo starting point. |
| 1.1 | April 16, 2026 | Added Section 0.0 (Pre-Build Housekeeping) covering the audit and archive prompts (0.0.1, 0.0.2). Discovered during execution that the repo at C:\Tool\AI-Schedule-Analysis-Solutions\ contained prior-build artifacts (app/, ollama/, scripts/, tests/, PHASE-COMPLETE-HARDENING.md) that needed archival before Prompt 0.1 could run safely. Prompt 0.1 updated with a precondition check. Recipe 1 and the cheat sheet updated to reflect the new starting sequence. |
| 1.2 | April 16, 2026 | Added Plan Mode tagging to every prompt. Each technique table now carries a 'Plan Mode: YES/NO' row at the top with a one-sentence reason, so Papisito can see at a glance whether to invoke Claude Code's Plan Mode before pasting. Amber band = YES, green band = NO. New cheat-sheet row added for the Plan-Mode-overruns-into-implementation failure mode. No changes to prompt text or section structure. |
| 1.3 | April 16, 2026 | Added the one-branch-per-phase standing rule (branches named claude/<phase-identifier>-YYYY-MM-DD, deleted on merge) after the scaffold commit had to be cherry-picked off a reused housekeeping branch. Added Prompt 0.5 (CI gate for pytest) to Section 0 after the archive commit left pytest tests/ failing on every PR during the rebuild window. Chose Option C: gate the pytest step on hashFiles('tests/**/*.py') != '' so CI auto-resumes when Phase 2 creates tests/. Cheat-sheet row added for 'CI is red on every PR and hiding real failures.' |

How to use this document as an anti-drift reference: When you suspect a chat session is hallucinating, deviating from the plan, or forgetting earlier decisions, load this document as an attachment and ask Claude to confirm its current proposal against the most recent edition. Mismatches between the proposal and the committed plan are the first signal that drift has occurred.

# How to Read This Guide

This guide teaches you how to prompt Claude Code to build revision 2 of the Schedule Forensics tool as a greenfield, multi-agent orchestrated rebuild. It is organized as four sections, each with a different audience, each with its own prompting patterns.

### The five sections

- Section 0.0 — Pre-Build Housekeeping. Added in Ed. 1.1. Two prompts that audit the repo's current state and archive prior-build artifacts before any skill scaffolding begins. Skip this section only if you are starting from a genuinely empty repository.

- Section 0 — Project-Knowledge Skill Development. How to prompt Claude Code to mine your project knowledge files (NASA handbooks, DCMA metrics, Lessons Learned, SSI driving slack, NID 7120.148, GPR 7120.7B) and convert them into reusable Claude Code skills the specialist agents can reference. This is the single biggest quality lever in the whole build.

- Section A — Orchestration Prompts. How to prompt the Lead / Coordinator agent to plan, delegate, and synthesize across specialist agents using Swarm Mode, Coordinator Mode, and the Leader / Pipeline / Council / Watchdog / Fan-Out patterns.

- Section B — Specialist Development Prompts. The prompts that individual agents receive for focused work: parser, CPM engine, DCMA metrics, forensic manipulation detection, frontend, testing, documentation, launcher / packaging.

- Section C — Runtime Analysis Prompts. The prompts your built tool will send to the schedule-analyst Ollama model (or Claude API toggle) at analysis time to generate the two separate report deliverables — the scheduler-grade forensic narrative and the judge / PM-grade plain-language report.

### Each prompt entry follows the same structure

Every prompt example in sections A, B, and C follows a consistent six-field pattern so you can scan, adapt, and deploy them without rereading the whole section:

- Why it works — the underlying mechanism, not just the surface rule.

- Example prompt — actual language tuned to your tool and your CUI constraints, ready to paste.

- When to use it — the specific problem shape this prompt solves.

- Common failure — how this prompt misfires and what to watch for.

- Best combos — which other prompts in this guide multiply its effect.

- Proficiency — your target skill level: Beginner, Intermediate, or Advanced.

### Plan Mode tag (added Ed. 1.2)

Every prompt in this guide also carries a Plan Mode recommendation at the top of its entry, color-coded for fast scanning. Plan Mode is a Claude Code feature that has Claude produce a written plan before executing any changes. It is useful on prompts with real architectural decisions and counterproductive on prompts that are already scripted step-by-step.

- Amber band / Plan Mode: YES — run this prompt in Plan Mode first. The prompt involves architectural choices, non-obvious implementation paths, or code volume large enough that you want to see the approach before context is spent.

- Green band / Plan Mode: NO — run this prompt without Plan Mode. The prompt is either prescriptive step-by-step (filesystem operations, git commands), an audit / review task with a fixed checklist, or the deliverable is itself a plan document and running Plan Mode would be recursive noise.

One failure mode of Plan Mode deserves a heads-up: Claude Code sometimes produces a plan that is 80% of the way to the actual implementation — hundreds of lines of pseudocode, elaborate justifications, suggested file layouts. That is a sign the plan has overrun its purpose. A good plan is skimmable in 30 seconds, names the decisions made, and leaves the actual writing for the execution phase. If you see a plan that looks like an implementation in disguise, interrupt with 'shorter plan, execute' before it finishes.

### Non-negotiable constraints this guide encodes

Every prompt in this document is written assuming the following are true. If any of these change, the prompts need to be re-audited before use.

- CUI-local only. Schedule data (.mpp, .xer, .xml, exported CSVs) never transmits to any cloud service. Ollama is the default analysis engine; Claude API is a toggle for unclassified work only.

- No admin rights on the target machine. Portable OpenJDK 21, portable Node.js, and Python 3.11+ run from OneDrive. No MSI installers. No services.

- MS Project is installed natively. Parser strategy is COM automation via win32com (primary) with MPXJ / JPype explicitly deprecated based on documented build failures.

- Cross-version task matching uses Unique ID, never Task ID. Task ID is a row number and reshuffles between versions. Unique ID is stable for the life of the task.

- Desktop shortcut launches via .bat (primary) with a .ps1 fallback documented. PowerShell execution policy bypass is pre-baked into the fallback target string.

- Two separate report deliverables. One forensic-analyst narrative for schedulers and attorneys; one plain-language report for federal magistrate judges, PMs, and high-level executives. Different prompts, different voices, different evidence density.

- No Earned Value Analysis in this phase. EVA is deferred to phase 3. Any agent that tries to include it is overstepping.

- One branch per phase (added Ed. 1.3). Every phase of the rebuild runs on its own feature branch named claude/<phase-identifier>-YYYY-MM-DD, branched fresh from main, squash-merged via PR, and deleted on merge. No branch hosts work from more than one phase. Recycling branches from completed work creates misleading git history and makes rebase scenarios harder than they need to be.

# The Core Mental Model for This Build

Claude Code, like any large language model, defaults toward agreeable, hedged, generic output. Every prompt in this guide works by fighting those defaults. Each prompt does one of four things:

- Narrows the response space — through persona, format, constraints, audience, and explicit institutional knowledge grounded in your NASA / DCMA / Lessons Learned sources.

- Forces better reasoning — through chain-of-thought decomposition, pre-mortem, rubric scoring, and explicit calculation methodology.

- Fights defaults — through anti-sycophancy instructions, negative constraints, pre-commitment guardrails, and critic mode review.

- Compounds quality across agents — through orchestration, self-critique, iterative refinement, and adversarial review.

When a prompt is underperforming, diagnose which of the four it lacks and add the matching technique. That is the whole game.

### One meta-rule that overrides everything else

Rule: Every metric, finding, and conclusion this tool produces must be traceable back to specific Unique IDs and specific field values in the source schedule(s). No opaque numbers. No unexplained conclusions. Every prompt in this guide must either enforce this rule or inherit it from a prompt that does. This is the difference between a tool that supports a forensic narrative in court and a tool that gets dismissed as a black box.

# Section 0.0 — Pre-Build Housekeeping

Before any skill scaffolding, orchestration planning, or specialist work begins, the repository's current state must be audited and any prior-build artifacts moved out of the active working tree. This section was added in Edition 1.1 after the initial run discovered that the repo at C:\Tool\AI-Schedule-Analysis-Solutions\ already contained a complete prior-build application tree (app/, ollama/, scripts/, tests/) plus phase-specific documentation (PHASE-COMPLETE-HARDENING.md).

Running Prompt 0.1 directly against a repo that still contains prior-build contents is the single most likely way to get Claude Code to conflate the old and new builds, invent a middle path neither version was designed for, and waste a session cleaning up the confusion. Two prompts, run in order and in separate sessions, eliminate that risk.

### Ordering

- Prompt 0.0.1 — audit only, read-only commands, produces a classification table for your review. No files moved.

- Human review gate — you personally review the classification and confirm what should be archived before Prompt 0.0.2 runs.

- Prompt 0.0.2 — archive execution using git mv (history preserved), with a RUNTIME-BROKEN-BY-ARCHIVE.md note that documents which runtime paths are expected to fail until the rebuild restores them.

## Prompt 0.0.1 — Pre-build repository audit

| Plan Mode | NO — Read-only audit with a fixed checklist. Plan mode adds no architectural decision to surface. |
| --- | --- |
| Why it works | An audit prompt that can modify files is not an audit — it's a migration. By restricting the audit session to read-only git and filesystem commands, and by requiring a classification table the human must approve before any destructive action, this prompt makes the audit step a genuine checkpoint rather than a rubber stamp. The classification table also surfaces prior-build decisions (e.g., is the existing CLAUDE.md a keeper or an archival candidate?) that you would otherwise discover mid-rebuild. |
| Example prompt | You are performing a pre-build housekeeping audit on the AI-Schedule-Analysis-Solutions repo at C:\Tool\AI-Schedule-Analysis-Solutions\. Context: this repo contains artifacts from prior build attempts. Before a new build begins, we need to (a) know exactly what is currently in the repo, (b) archive the prior-build artifacts into a clearly labeled folder so they are preserved but out of the way, and (c) confirm the workspace is ready for a fresh skill library scaffold. You are NOT building anything in this session. You are auditing, archiving, and reporting. Perform these steps in order: STEP 1 — Inventory Run git status and git log --oneline -20 to capture current repo state. Then produce a complete tree listing of the repo's top two directory levels (depth=2), excluding anything already in .gitignore. Show me what is actually there. STEP 2 — Classify every top-level item into one of three buckets For each file or directory at the repo root, classify it: - KEEP: required for the rebuild (.gitignore, .git/, README.md, requirements.txt, run.bat, run.sh, .github/ if it has workflows, CLAUDE.md if it exists) - ARCHIVE: artifact from a prior build attempt that should be preserved but moved out of the active working tree (PHASE-COMPLETE-HARDENING.md, any phase-specific docs, old app/ contents, old ollama/ contents, old scripts/ contents, old tests/, any existing .claude/skills/ directory contents) - DECIDE: items where you are not certain — flag these for my decision rather than auto-classifying Produce the classification as a markdown table with columns: Item ¦ Type (file/dir) ¦ Size ¦ Bucket ¦ Reasoning. STEP 3 — Stop and wait After producing the classification table, STOP. Do not move anything. Do not delete anything. Do not create the archive folder yet. Do not run git commands beyond read-only inspection. I will review your classification and tell you which items to actually archive before you proceed. Rules for this session: - Do not modify any file. - Do not run git add, git commit, git mv, git rm, or any destructive command. - Do not create, rename, or delete any directory. - Read-only commands only: git status, git log, dir, tree, cat, type, ls, pwd. - If you find a .claude/skills/ directory already populated with content, flag it prominently in STEP 2 as a BLOCKING item requiring my decision before any skill scaffolding work can begin. - If you find any .mpp, .xer, .xml, .mpx, or .pmxml file anywhere in the repo, flag it as a CUI VIOLATION regardless of whether .gitignore is currently excluding it — these files should never be in the working tree. Report format: 1. Git status summary 2. Recent commit history (last 20) 3. Full tree listing (depth 2) 4. Classification table 5. Any BLOCKING items or CUI VIOLATIONS flagged 6. Your recommended action (what you would archive if I authorized it) — but do not execute the action. Stop after reporting. Wait for my decision on what to archive. |
| When to use | The first Claude Code session of the rebuild, before any other work. Run once per rebuild attempt — if the rebuild gets abandoned and restarted later, rerun this prompt against whatever state the repo is in at that moment. |
| Common failure | Claude Code treats 'audit' as an invitation to start cleaning up the repo and makes read-ahead edits. Counter by the explicit 'read-only commands only' list and by requiring the STOP at end of step 2. |
| Best combos | Prompt 0.0.2 (archive execution) immediately after, once you have reviewed the classification table. |
| Proficiency | Beginner |

## Prompt 0.0.2 — Archive prior-build artifacts

| Plan Mode | NO — Scripted filesystem operations with git mv commands enumerated in the prompt. No architectural choice. |
| --- | --- |
| Why it works | Moving files with plain mv or rm+add loses git history. Using git mv preserves the renames in history so future investigators can follow what moved where. The added pre-flight checks (grep run.bat and ci.yml for references to the folders being archived) surface the expected consequences BEFORE the archive happens, so the RUNTIME-BROKEN-BY-ARCHIVE.md note is honest and specific rather than generic. |
| Example prompt | You are executing the archive phase of the pre-build housekeeping on AI-Schedule-Analysis-Solutions at C:\Tool\AI-Schedule-Analysis-Solutions\. A prior audit session classified five root-level items as ARCHIVE: - PHASE-COMPLETE-HARDENING.md - app/ (entire tree) - ollama/ (entire tree) - scripts/ (entire tree) - tests/ (entire tree) (Adjust this list to match YOUR audit output if it differs. The list below is the one produced by the initial rebuild attempt on 2026-04-16 and is the default.) KEEP items (must not be touched): - .git/, .gitignore, .claude/ (contains CLAUDE.md only), .github/, README.md, requirements.txt, run.bat, run.sh Your task this session is to move those items into a dated archive folder, preserving git history via git mv, and to document the consequences clearly. You are NOT scaffolding skills, NOT rebuilding anything, NOT editing any file outside of the archive move and the documentation note described below. Perform these steps in order. Stop if any step fails unexpectedly. STEP 1 — Pre-flight verification (read-only) Before moving anything, run the following read-only checks and report the output: a. git status (must report a clean working tree on your current branch) b. git branch (report which branch you are on) c. Grep run.bat and run.sh for references to 'app', 'scripts', 'ollama', 'tests' and report any matches verbatim. This tells us what the launcher will break. d. Grep .github/workflows/ci.yml for the same terms. Report matches. This tells us what CI will break. If git status is not clean, STOP and report — do not proceed to archiving. If any grep returns matches, record them in a list for STEP 4. STEP 2 — Create the archive folder Create directory archive/prior-build-YYYY-MM-DD/ at the repo root, substituting today's date. Create an empty .gitkeep file inside it so the directory is trackable before contents arrive. STEP 3 — Move each ARCHIVE item using git mv Use git mv (not mv, not rm+add) so history is preserved. Run one command per item, stopping immediately if any fails. Example commands (adjust paths to match your audit's ARCHIVE list): git mv PHASE-COMPLETE-HARDENING.md archive/prior-build-YYYY-MM-DD/PHASE-COMPLETE-HARDENING.md git mv app archive/prior-build-YYYY-MM-DD/app git mv ollama archive/prior-build-YYYY-MM-DD/ollama git mv scripts archive/prior-build-YYYY-MM-DD/scripts git mv tests archive/prior-build-YYYY-MM-DD/tests After the moves, run git status and confirm the output shows only renames and nothing else. If anything else appears in the diff, STOP and report. STEP 4 — Write the broken-runtime note Create a file at archive/prior-build-YYYY-MM-DD/RUNTIME-BROKEN-BY-ARCHIVE.md with this exact structure: # Runtime Broken By This Archive This archive moved N items out of the active working tree on YYYY-MM-DD as part of the rebuild housekeeping. The following runtime paths are BROKEN as a result and will remain broken until the corresponding phases of the rebuild complete and restore equivalent functionality. ## Launcher references into archived directories [Paste here the verbatim grep matches from STEP 1c. If there were no matches, write "No references found in run.bat or run.sh — launcher does not call into any archived directory."] ## CI references into archived directories [Paste here the verbatim grep matches from STEP 1d. If no matches, write "No references found in .github/workflows/ci.yml."] ## Expected restoration - app/ restored by rebuild Phases 2-11 - tests/ restored incrementally alongside each phase - ollama/ restored by rebuild Phase 10 - scripts/ superseded by rebuild Phase 12 (run.ps1 at repo root) - PHASE-COMPLETE-HARDENING.md preserved here for reference; not restored Do not attempt to run run.bat or run.sh against this repo state expecting the old behavior. The launcher will fail. This is expected. The rebuild will produce a new launcher in Phase 12 that points at the rebuilt app/ tree. STEP 5 — Commit Stage the archive move and the note together and commit with a message that references the dated archive folder. Report the commit hash. STEP 6 — Final state verification Run these read-only commands and report output: a. dir (or ls -la) at the repo root — confirm root now contains only KEEP items plus the new archive/ directory b. git log --oneline -3 c. git status — should be clean STEP 7 — Stop Do not push to origin in this session. Pushing is my decision, not yours. Do not create .claude/skills/ — that is the next session's job. Do not modify any KEEP item. Stop after reporting. Await my instruction on whether to push to origin and whether to proceed with skill library scaffolding. |
| When to use | Immediately after Prompt 0.0.1 completes and you have reviewed its classification table. One session. |
| Common failure | Agent uses mv or rm+add instead of git mv and loses history. Counter by naming git mv explicitly in each command example and by requiring git status output that shows only renames. |
| Best combos | Prompt 0.0.1 produces the classification this prompt acts on; Prompt 0.1 runs next (with its new precondition check for the archive folder's existence). |
| Proficiency | Beginner |

# Section 0 — Project-Knowledge Skill Development

Before any specialist agent writes a line of code, Claude Code needs a library of institutional knowledge skills derived from your project files. Without this step, every agent is pattern-matching on generic scheduling knowledge instead of NASA-specific, DCMA-specific, forensic-specific domain knowledge. This section teaches you how to build that skill library.

### What a Claude Code skill is

A Claude Code skill is a directory containing a SKILL.md file plus supporting reference material (markdown, code, schemas). When an agent's task triggers the skill's description keywords, Claude Code automatically loads SKILL.md into the agent's context. The agent then has authoritative, project-specific guidance without burning tokens re-explaining the domain every time.

For this build, skills are how we encode the content of your project knowledge files — NASA handbooks, DCMA metrics, NID 7120.148, GPR 7120.7B, Lessons Learned, SSI driving slack, Acumen Metric Developer's Guide — into reusable, version-controlled references that survive across Claude Code sessions.

### The skill library to build

Build these eight skills, in this order, before any specialist development begins:

| # | Skill Name | Source File(s) and Purpose |
| --- | --- | --- |
| 1 | nasa-schedule-management | Source: schedule-management-handbook-20240315-update.pdf. Purpose: Agency best practices, required schedule components, compliance checks, lessons learned archival patterns. |
| 2 | nasa-program-project-governance | Source: NID_7120_148_.pdf, N_PR_8000_004C_.pdf, GPR_7120_7B_Admin_Ext_08_09_2023.pdf, NASA_Acronyms.pdf. Purpose: Governance framework references, approval paths, acronym translation for reports. |
| 3 | dcma-14-point-assessment | Source: DeltekDECMMetricsJan2022.xlsx, DeltekAcumen88MetricDevelopersGuide.pdf. Purpose: All 14 metrics with formulas, thresholds, exclusions from denominator, pass/warn/fail semantics. |
| 4 | driving-slack-and-paths | Source: SSINASAunderstandingdrivingslack.pdf. Purpose: Driving slack definition, driving path trace algorithm, relationship slack calculation, why driving slack is more accurate than total float for CPM tracing. |
| 5 | forensic-manipulation-patterns | Source: Schedule_Forensics_Lessons_Learned.md plus synthesized industry knowledge. Purpose: The 10 manipulation detection patterns (driving path swap, lag laundering, constraint pinning, duration smoothing, baseline tampering, actuals rewriting, progress inflation, logic deletion, float harvesting, summary-logic abuse) with evidence requirements. |
| 6 | mpp-parsing-com-automation | Source: Schedule_Forensics_Lessons_Learned.md Appendix D. Purpose: win32com COM automation pattern, the ten documented gotchas, zombie process cleanup, dialog suppression, field-level validation methodology. |
| 7 | acumen-reference | Source: DeltekAcumen88TechnicalOverviewandSystemRequirements.pdf, DeltekAcumen88QuickStartGuide.pdf, DeltekAcumen88APIGuide.pdf, DeltekAcumen88ReleaseNotes.pdf, DeltekAcumen88CostDataCsvStructure.pdf. Purpose: Reference-only context on Acumen's forensic module and data structures; our tool is not an Acumen replacement but must be credible in the same conversations. |
| 8 | cui-compliance-constraints | Source: Your memory plus derived from the build directive. Purpose: What files never leave the machine, what libraries are forbidden (telemetry, cloud uploaders), what data can go to Claude API vs. Ollama, gitignore patterns, launcher isolation rules. |

## Prompt 0.1 — Create the skill scaffold

Precondition (added Ed. 1.1): Before running this prompt, Section 0.0 (Pre-Build Housekeeping) must be complete. At minimum, the repo root must contain only the KEEP items plus an archive/ directory. If .claude/skills/ already exists with content, do not run this prompt until that content is archived or explicitly approved to carry forward.

| Plan Mode | NO — Pure filesystem scaffolding — eight empty directories and eight stub files. The prompt is already the plan. |
| --- | --- |
| Why it works | Telling Claude Code to build all eight skills at once produces shallow, boilerplate SKILL.md files with placeholder descriptions. Scaffolding first — creating the directory structure, empty SKILL.md stubs, and a skills/README.md index — forces Claude Code to commit to the taxonomy before investing in content. If the taxonomy is wrong, you catch it before hours of content work. |
| Example prompt | You are setting up the skill library for the AI-Schedule-Analysis-Solutions repo at C:\Tool\AI-Schedule-Analysis-Solutions\. Your task in this session is SCAFFOLDING ONLY. Do not populate skill content yet. Do not write any skill bodies. Only create the directory structure and placeholder files. PRECONDITION CHECK — perform before any scaffolding work: - Verify that an archive/prior-build-*/ directory exists at the repo root. If it does not, STOP and report that pre-build housekeeping (Prompts 0.0.1 and 0.0.2) has not been completed. - Verify that .claude/skills/ either does not exist or is empty. If it exists with content, STOP and report — we do not overwrite existing skill content. - Verify that git status reports a clean working tree on your current branch. If not, STOP. If all three preconditions pass, proceed with scaffolding: Perform these steps and stop: 1. Create directory .claude/skills/ at the repo root if it does not exist. 2. Inside .claude/skills/, create eight subdirectories, one per skill: - nasa-schedule-management/ - nasa-program-project-governance/ - dcma-14-point-assessment/ - driving-slack-and-paths/ - forensic-manipulation-patterns/ - mpp-parsing-com-automation/ - acumen-reference/ - cui-compliance-constraints/ 3. In each subdirectory, create a SKILL.md file with YAML frontmatter only (name, description placeholder of 1-2 sentences, license "Proprietary — polittdj / AI-Schedule-Analysis-Solutions"). Body of each SKILL.md can be a single line: "# [Skill Title]\n\nContent to be populated." 4. Create .claude/skills/README.md that lists all eight skills with one-line descriptions and a note that content is populated by subsequent sessions. 5. Commit with message: "Scaffold skill library — 8 skills, placeholders only, content TBD". Do not write skill content. Do not edit any files outside .claude/skills/. If you finish the scaffold and have context remaining, STOP and report completion rather than starting to fill in any skill body. Report back with: - The full directory listing under .claude/skills/ - The commit hash - Any deviation from the instruction above (there should be none). |
| When to use | The very first Claude Code session of the rebuild, before any agent work. Gets the taxonomy locked down so every subsequent session has a stable place to put institutional knowledge. |
| Common failure | Claude Code gets enthusiastic and starts writing real skill content because eight empty directories feel anticlimactic. Counter this by being explicit that scaffolding means scaffolding and that finishing early is a success, not a failure. |
| Best combos | Prompt 0.2 (populate one skill at a time) immediately after; Prompt A.1 (orchestrator plan) once the scaffold exists. |
| Proficiency | Beginner |

## Prompt 0.2 — Populate a single skill from your project knowledge

| Plan Mode | YES — Claude Code must decide how to structure a 1500-3000 word skill file from multiple source documents. Worth seeing the approach before it burns context on content. |
| --- | --- |
| Why it works | Populating all eight skills in one session overruns Claude Code's context window and produces thin, generic content in the skills at the end of the session. One skill per session lets Claude Code spend its full context budget on a single PDF or document, producing content that actually captures the source material's specificity. This is the same phase-gated discipline your Lessons Learned document demands for the parser rebuild. |
| Example prompt | You are populating a single Claude Code skill. Target skill: dcma-14-point-assessment. Context files available to you in this session: - DeltekDECMMetricsJan2022.xlsx (Deltek's DECM metric library with thresholds) - DeltekAcumen88MetricDevelopersGuide.pdf (metric calculation methodology) - schedule-management-handbook-20240315-update.pdf (NASA's view of DCMA-aligned metrics) Your task: read all three files, then rewrite .claude/skills/dcma-14-point-assessment/SKILL.md as a comprehensive, authoritative reference that any specialist agent in a later session can use to implement a DCMA 14-point assessment module. SKILL.md must contain, at minimum: 1. YAML frontmatter with a precise "description" field that will cause Claude Code to load this skill when an agent's task mentions: DCMA, 14-point, schedule quality metrics, missing logic, leads, lags, high float, negative float, high duration, BEI, CPLI, missed actuals, critical path test. Description must be under 500 characters. 2. An overview of what DCMA 14-point is and when it applies. 3. For EACH of the 14 metrics: a. Metric name and number (1-14). b. Plain-language definition. c. Exact formula, including numerator and denominator specification. d. Tasks excluded from the denominator (LOE, summary, milestones, completed tasks) — per DCMA-EA PAM 200.1 Section 4. e. Pass / Warn / Fail thresholds with the specific numeric values from Deltek DECM. f. Interpretation guidance: what a failed metric means as a forensic signal, not just a quality signal. g. Known false-positive patterns where the metric is "red" but there is a legitimate defense. 4. A section on "investigative triggers, not automatic failures" — red metrics are the START of a forensic investigation, not the conclusion. 5. A "drill-down requirement" section stating that every metric value in the final output must be accompanied by the list of Unique IDs that triggered it. 6. A references section citing the source documents by filename. Do not invent threshold values. If DECM and the NASA handbook disagree on a threshold, report both with attribution. If you cannot find a specific value for a specific metric, say so explicitly rather than guessing. Length target: 1500-3000 words. Denser is better than longer. When complete, commit with message: "Populate dcma-14-point-assessment skill from DECM + Acumen + NASA handbook sources". |
| When to use | One Claude Code session per skill, run eight times total. Sessions 2 through 9 of the rebuild if you're counting sequentially. |
| Common failure | Claude Code pulls generic DCMA knowledge from training data instead of reading your specific source files, producing a SKILL.md that looks authoritative but contradicts Deltek DECM's actual thresholds. Counter this by naming the files explicitly and instructing that disagreement between sources must be reported rather than resolved by Claude. |
| Best combos | Prompt 0.3 (skill validation) run against each populated skill before moving to the next. |
| Proficiency | Intermediate |

## Prompt 0.3 — Validate a populated skill before committing

| Plan Mode | NO — Adversarial audit with a fixed checklist. Plan mode would recapitulate the checklist. |
| --- | --- |
| Why it works | Populating a skill and validating a skill are different cognitive tasks, and letting one agent do both creates a blind spot — the agent that wrote the content is the wrong agent to catch its own errors. This prompt invokes a fresh context to audit a skill file adversarially, which is the same pattern your forensic tool applies to schedule manipulation: the person making the change cannot be the person reviewing the change. |
| Example prompt | You are an adversarial reviewer auditing a Claude Code skill file that another agent just populated. Your job is to find problems, not to be helpful. File under review: .claude/skills/dcma-14-point-assessment/SKILL.md Also available to you: - The original source files: DeltekDECMMetricsJan2022.xlsx, DeltekAcumen88MetricDevelopersGuide.pdf, schedule-management-handbook-20240315-update.pdf Audit checklist — for each item, report PASS, FAIL, or UNVERIFIABLE with evidence: 1. Every numeric threshold in SKILL.md cites the specific source file it came from. 2. No threshold value appears in SKILL.md that cannot be traced back to one of the source files. (If you find an uncited number, that is a FAIL — flag it.) 3. All 14 metrics are present and numbered. 4. For each metric, exclusions from the denominator are explicitly listed (LOE, summary, milestones, completed). 5. No metric's formula contradicts the source documents. If it does, quote both the SKILL.md language and the source language side by side. 6. The skill's YAML description field contains keywords that would actually cause Claude Code to load this skill when relevant (DCMA, 14-point, metric names). Test: would a prompt about "check the schedule's leads and lags" trigger this skill? If not, the description is broken. 7. The "investigative trigger, not automatic failure" guidance is present and clearly stated. 8. The "drill-down requirement" (every metric value accompanied by Unique IDs) is present. Report format: - One section per audit item, each with PASS/FAIL/UNVERIFIABLE and one-paragraph evidence. - A summary verdict at the end: APPROVE, REVISE (list specific edits), or REJECT (skill needs rewrite). Do not make any file changes. Your job is audit-only. If the verdict is APPROVE, I will run a separate prompt to commit. If REVISE, I will apply your edit list and re-run this audit. If REJECT, we restart from Prompt 0.2. |
| When to use | Run immediately after each Prompt 0.2 session, before moving to the next skill. Treat this as a gate: no skill moves to 'done' status until it passes. |
| Common failure | The reviewer agent acts like a cheerleader and rubber-stamps the file. Counter this by being explicit about finding problems, not being helpful, and by requiring specific evidence (quoting both the SKILL.md text and the source text) rather than vague approvals. |
| Best combos | Prompt 0.2 (populate) feeds this prompt; this prompt's output feeds back into a revised 0.2 invocation if the verdict is REVISE. |
| Proficiency | Intermediate |

## Prompt 0.4 — Cross-skill consistency check

| Plan Mode | NO — Cross-skill consistency check with seven named high-risk topics. The checklist is the plan. |
| --- | --- |
| Why it works | Individual skills can each be correct while the skill library as a whole is contradictory. For example, nasa-schedule-management and dcma-14-point-assessment can disagree on whether LOE tasks belong on the critical path (they don't, per both sources, but a sloppy population could let one skill say 'exclude' and the other say 'flag'). This prompt checks the library as a system after all eight skills are populated. |
| Example prompt | You are performing a cross-skill consistency audit on the .claude/skills/ library. All eight skills are now populated. Your job: identify any place where two or more skill files make claims that contradict each other, OR where the same concept is defined differently in different skills. Specifically check for contradictions or inconsistencies on these high-risk topics: 1. What counts as a "completed task" for DCMA exclusion purposes. (dcma-14-point-assessment vs. mpp-parsing-com-automation) 2. Whether and how LOE tasks appear on the critical path. (nasa-schedule-management vs. dcma-14-point-assessment vs. driving-slack-and-paths) 3. Unique ID vs. Task ID for cross-version matching. (mpp-parsing-com-automation vs. forensic-manipulation-patterns) 4. Hard constraint detection thresholds. (dcma-14-point-assessment vs. nasa-schedule-management vs. forensic-manipulation-patterns) 5. What data is allowed to leave the local machine. (cui-compliance-constraints vs. every other skill) 6. Status date handling — how a null / NA / sentinel Status Date is treated. (mpp-parsing-com-automation vs. forensic-manipulation-patterns) 7. Driving slack vs. total float as the CPM tracing basis. (driving-slack-and-paths vs. any other skill that mentions critical path) For each contradiction found: - Quote both skills' language verbatim. - Identify which source document each skill is relying on. - Recommend which language should win and which should be edited, with reasoning. If no contradictions are found on a given topic, say "No contradiction on topic N — [one-sentence reason]." Produce a consolidated edit list at the end: exactly which files need which edits to resolve the contradictions. Do not make the edits. I will run a separate prompt to apply them one at a time. |
| When to use | Run once, after all eight skills are populated and individually validated via Prompt 0.3. |
| Common failure | Agent reports 'no contradictions found' because it did not actually read both skills carefully. Counter by naming the seven specific high-risk topics and requiring verbatim quotes, which forces the agent to open both files. |
| Best combos | Prompt 0.3 (individual skill audit) runs before this; this prompt's output feeds a series of targeted edits. |
| Proficiency | Advanced |

## Prompt 0.5 — Gate CI pytest step on tests/ existing (added Ed. 1.3)

Context: After the Ed. 1.1 archive commit moved tests/ into archive/prior-build-2026-04-16/, the CI workflow's pytest step failed on every subsequent PR with 'path not found'. This hid real regressions in a sea of expected-red noise. This prompt repairs CI during the rebuild window so every red X from this point forward means a real failure worth investigating. The pytest step auto-resumes the moment Phase 2 (parser) creates tests/ at the repo root.

| Plan Mode | NO — a scoped YAML edit with exact before/after text and known line number. No architectural decision to surface. |
| --- | --- |
| Why it works | The alternatives (delete the pytest step, comment it out, branch-filter it) all require a manual un-disable step later when the rebuild restores tests/. Using GitHub Actions' hashFiles() as an if-condition means CI heals itself the moment any rebuild phase commits a single test file at the expected path. No human memory required. |
| Example prompt | You are repairing the CI workflow on AI-Schedule-Analysis-Solutions at C:\Tool\AI-Schedule-Analysis-Solutions\. Problem: .github/workflows/ci.yml runs `python -m pytest tests/ -v --tb=short` on every push and PR. The archive commit moved tests/ to archive/prior-build-2026-04-16/tests/, so every CI run fails with "path not found" until the rebuild restores a tests/ directory. This hides real regressions in a sea of expected-red builds. Fix: gate the pytest step on the tests/ directory existing at the repo root. The moment any future rebuild phase creates tests/, CI will start running tests again automatically. STEP 1 — Pre-flight a. git status (must be clean) b. git branch --show-current (should be main) c. git log --oneline -3 If not on main or working tree dirty, STOP. STEP 2 — Create feature branch git checkout -b claude/ci-gate-pytest-on-tests-dir-YYYY-MM-DD STEP 3 — Read the current workflow cat .github/workflows/ci.yml Find the step that runs pytest. Report the EXACT surrounding context (the step's name, the preceding `- name:` line, any `if:` condition already present). Do not edit yet. STEP 4 — Apply the edit Modify the pytest step to run only when tests/ exists at the repo root: Before: - name: Run tests run: python -m pytest tests/ -v --tb=short After: - name: Run tests if: hashFiles('tests/**/*.py') != '' run: python -m pytest tests/ -v --tb=short Preserve whatever name is actually in your workflow (may not be "Run tests"). Indentation: the if-condition goes at the same indent as name and run, two spaces deeper than the step's dash. Do not modify any other step. If other references to archived paths (app/, ollama/, scripts/) appear in ci.yml, FLAG them in your report but DO NOT fix them in this session. STEP 5 — Verify YAML syntax python -c "import yaml; yaml.safe_load(open('.github/workflows/ci.yml'))" git diff .github/workflows/ci.yml STEP 6 — Commit git add .github/workflows/ci.yml git commit -m "ci: gate pytest step on tests/ existing at repo root" STEP 7 — Push and open PR git push -u origin claude/ci-gate-pytest-on-tests-dir-YYYY-MM-DD Then via gh CLI or GitHub MCP tooling: - PR title: "ci: gate pytest on tests/ existing — fix red CI during rebuild window" - Squash-merge with branch delete after merge STEP 8 — Verify CI is green on main Watch the CI run post-merge. Expected: pytest step skipped (tests/**/*.py matches nothing), other steps run normally, overall conclusion "success". If CI is still red, STOP and report what failed. STEP 9 — Clean up git checkout main && git pull origin main git log --oneline -5 git branch -a (feature branch should be gone) git status (clean) STEP 10 — Stop Do not start any other work. Report: current workflow pytest context, diff, commit SHA, PR URL, merge SHA, post-merge CI conclusion, final state, any deviations or flagged items. |
| When to use | Run once, immediately after the skill library scaffold commit is merged to main (before any skill population work begins). Earlier if CI red is blocking a review. Later only if you are comfortable with CI red on every PR for the duration. |
| Common failure | Agent edits the wrong step or adds the if-condition at the wrong indentation level, producing invalid YAML. Counter by requiring the verbatim before/after diff in the report and requiring a YAML-load validation step before commit. |
| Best combos | Runs after Prompt 0.1 (scaffold) is on main; runs before Prompt 0.2 (populate first skill) so that the first skill-population PR gets a clean green CI signal. |
| Proficiency | Beginner |

# Section A — Orchestration Prompts

Orchestration prompts are for the Lead / Coordinator agent. They tell that agent how to plan, delegate, and synthesize across the specialist agents. You paste these into Claude Code. The Lead agent then writes the prompts for the specialists.

The orchestration patterns used in this guide are:

- Leader pattern — one coordinator agent plans the work, delegates to specialists, and integrates results.

- Pipeline pattern — specialists run in a fixed sequence, each consuming the previous agent's output.

- Council pattern — multiple specialists independently review the same artifact, then the coordinator reconciles.

- Fan-Out pattern — coordinator delegates N parallel independent tasks, then aggregates.

- Watchdog pattern — a dedicated agent watches for scope drift, CUI leakage, or constraint violation during other agents' work.

## Prompt A.1 — The master orchestration plan

| Plan Mode | NO — The deliverable is itself a plan document (BUILD-PLAN.md). Plan mode on top of a planning prompt is recursive noise. |
| --- | --- |
| Why it works | Before any specialist agent is invoked, the coordinator needs a written plan that commits to an ordering, identifies dependencies, and names explicit gates. Without this artifact, every subsequent Claude Code session has to re-derive the plan from context, which wastes tokens and produces drift. A committed plan also gives you — Papisito — something concrete to push back on before work starts. |
| Example prompt | You are the Lead Coordinator agent for the Schedule Forensics greenfield rebuild. Your repo is at C:\Tool\AI-Schedule-Analysis-Solutions\ and the skill library at .claude/skills/ is fully populated and validated. You are NOT building anything in this session. Your job is to produce the master plan document, commit it, and stop. Produce a file at docs/BUILD-PLAN.md containing: 1. Executive summary — one paragraph on scope, non-goals, and success criteria. 2. Architecture decisions committed — enumerate and justify: - Parser: win32com COM automation primary, MPXJ subprocess fallback, XML import last resort - Backend: Flask on localhost:5000 (not FastAPI — matches the current repo's convention) - Frontend: server-rendered Jinja templates + htmx for interactivity (no React build chain, keeps the no-admin-rights constraint intact) - Analysis engine: pure Python, no external compute services - AI layer: Ollama (schedule-analyst custom model built on qwen2.5:7b-instruct) as default, Claude API toggle for unclassified work - Launcher: run.bat (primary), run.ps1 (fallback with ExecutionPolicy Bypass), both callable from a desktop .lnk shortcut - Report output: DOCX and XLSX via python-docx and openpyxl; PDF via the docx-to-pdf conversion already established 3. Work breakdown into phases — list the phases below in order, and for EACH phase name: - The specialist agent(s) who own it - The orchestration pattern used (Leader / Pipeline / Council / Fan-Out) - The input artifacts required from prior phases - The output artifacts produced - The explicit "done" criterion — what must be true to exit the phase - The validation prompt that gates exit Phases: Phase 1: Repo audit and harvest — inventory what exists in the current repo, identify keepers vs. archivables. Your memory says the repo has .claude/, .github/, app/, ollama/, scripts/, tests/, run.bat, run.sh, requirements.txt, README.md, PHASE-COMPLETE-HARDENING.md — treat these as data for the audit, not assumptions for the rebuild. Phase 2: Parser — COM automation module, proven working against a real .mpp before any analysis code Phase 3: Data model — Pydantic schemas for Task, Relationship, Calendar, ScheduleVersion Phase 4: CPM + driving path engine Phase 5: Multi-version matcher (by Unique ID) Phase 6: DCMA 14-point module Phase 7: NASA compliance module Phase 8: Forensic manipulation detection module (the 10 patterns from the forensic-manipulation-patterns skill) Phase 9: Report generator (two deliverables: scheduler-grade and judge-grade) Phase 10: AI narrative layer (Ollama primary, Claude API toggle) with the two runtime prompt templates from Section C Phase 11: Web UI (Flask + Jinja + htmx) with single-window design Phase 12: Launcher hardening — run.bat, run.ps1, desktop shortcut target string Phase 13: End-to-end integration test with a synthetic two-version schedule Phase 14: Documentation — CLAUDE.md (for future Claude sessions), README.md (human-readable), end-user install manual hook 4. CUI gates — name every phase where CUI exposure is possible and the specific control that prevents leakage. Parsing is the biggest risk; naming test files second. 5. Risk register — your three biggest risks from prior build attempts per Schedule_Forensics_Lessons_Learned.md, plus the mitigations baked into this plan. 6. Out of scope for this phase — enumerate explicitly: no Earned Value Analysis, no Acumen integration, no multi-user support, no cloud deployment, no admin-required installers. Do not start Phase 1 work. Commit BUILD-PLAN.md and stop. Your next session will start with Phase 1 using Prompt A.2. |
| When to use | First orchestration session, immediately after the skill library is populated and validated. Run once. Never skip. |
| Common failure | Coordinator agent proceeds to start Phase 1 because the plan seems obvious. Counter by being explicit that the plan is the deliverable and that starting Phase 1 is a violation of the prompt. |
| Best combos | Prompt A.2 (phase kickoff) uses this plan as its authoritative reference; Prompt 0.1 (skill scaffold) must complete before this runs. |
| Proficiency | Advanced |

## Prompt A.2 — Phase kickoff with Leader pattern

| Plan Mode | YES — Claude Code drafts three derivative prompts per phase. Worth seeing which scope decisions it makes before it commits prompt text to disk. |
| --- | --- |
| Why it works | A phase kickoff is where scope creep is born. If the coordinator just says 'start phase 3,' the agent will read the plan, form its own interpretation, and quietly expand scope. Forcing the coordinator to write a phase-specific prompt that references BUILD-PLAN.md explicitly, enumerates exit criteria, and names the validation prompt prevents that drift. |
| Example prompt | You are the Lead Coordinator. You are starting Phase 4: CPM + driving path engine. Per docs/BUILD-PLAN.md, Phase 4 requires: - Input: validated parser module from Phase 2 (backend/mpp_parser.py), Pydantic schemas from Phase 3 (backend/schemas.py) - Output: backend/cpm.py and backend/driving_path.py, both with test files in tests/ - Done criterion: tests pass for forward pass, backward pass, all 4 relationship types (FS, SS, FF, SF), leads, lags, and all 6 constraint types (SNET, SNLT, FNET, FNLT, MSO, MFO). Driving path trace validated against at least one synthetic 50-task network and one hand-calculated reference. Your job in THIS session is to: 1. Read docs/BUILD-PLAN.md Phase 4 section verbatim and confirm you understand the scope. 2. Read backend/mpp_parser.py and backend/schemas.py so you know the data model you're consuming. 3. Load the driving-slack-and-paths skill — its content must drive the driving_path.py implementation. 4. Write the Phase 4 specialist prompt that I will hand to a fresh agent. That specialist prompt must: - Be entirely self-contained (the specialist cannot see this session) - Reference the skill library by name - Enumerate the exact functions to implement with their signatures - Specify the test suite requirements, including the synthetic 50-task network the tests run against - Include the "no analysis without validated parser" rule from Schedule_Forensics_Lessons_Learned.md - End with explicit STOP conditions (when the specialist should stop and hand back for review) 5. Draft the Phase 4 validation prompt (Council pattern) that will run after the specialist completes — two independent reviewer agents, one focused on correctness vs. MS Project's output, one focused on edge cases (blank rows, circular logic, negative float). Output all three prompts into docs/phase-prompts/phase-04-*.md (three files). Do not invoke any specialist. Do not write any backend code. Commit and stop. I will personally review your three phase-04 prompts before any specialist work begins. |
| When to use | At the start of every phase from Phase 2 onward. Phase 1 (repo audit) can be kicked off directly since it has no predecessor phase. |
| Common failure | Coordinator writes the phase prompt AND invokes the specialist in the same session, which skips your human review gate. Counter by making 'do not invoke any specialist' an explicit STOP in the prompt, not a footnote. |
| Best combos | Prompt A.1 (master plan) is the authoritative reference this prompt reads; Prompt A.3 (specialist invocation) uses the phase-specific prompt this produces. |
| Proficiency | Advanced |

## Prompt A.3 — Council review pattern for high-risk modules

| Plan Mode | NO — Council review pattern with three fixed lenses. Plan mode adds no decision surface. |
| --- | --- |
| Why it works | For modules where a silent error propagates into every downstream conclusion — parser, CPM engine, manipulation detector — one reviewer is not enough. The Council pattern runs two or three reviewers with different focus lenses, then reconciles their findings. This mirrors forensic practice: you don't rely on one expert witness when the stakes are high. |
| Example prompt | You are the Lead Coordinator. Phase 2 (parser) has just completed its specialist implementation. Before accepting the module, you are running a Council review. Your task this session: invoke THREE independent reviewer agents, each with a narrow lens, then reconcile their findings into a single verdict. Reviewer 1 — Correctness lens: "You are auditing backend/mpp_parser.py for correctness. Your only job is to verify that the parser returns the same values MS Project itself returns for the same file. Specifically verify: Unique ID preservation, Status Date extraction (including null / NA / sentinel date handling per the mpp-parsing-com-automation skill), duration in minutes vs. working days conversion, TotalSlack sign semantics, calendar ID association for each task, and all four relationship types with correct From/To direction. Do not check style. Do not check performance. Only correctness. Produce a findings list; for each finding, cite the specific line in the parser and the specific gotcha from the mpp-parsing-com-automation skill that the parser violates or correctly handles." Reviewer 2 — Edge case lens: "You are auditing backend/mpp_parser.py for edge case handling. Enumerate the edge cases listed in the mpp-parsing-com-automation skill (blank rows returning None in the Tasks collection, zombie MSPROJECT.EXE process on crash, ReadOnly=True enforcement, dialog box suppression via DisplayAlerts=False, CoInitialize/CoUninitialize pairing, absolute path handling). For each edge case, state whether the parser handles it, and if so, cite the specific code. If any edge case is unhandled, that is a finding." Reviewer 3 — CUI lens: "You are auditing backend/mpp_parser.py for CUI compliance. Verify: no network calls, no telemetry libraries imported, no logging of file contents to any location outside the session's own stdout, no persistence of parsed data to any path other than in-memory or under the explicitly designated session directory. If you find any I/O that writes parsed data to disk, that is a finding unless it is gated by explicit user consent and written to a path under session_manager's control. Cite line numbers." After all three reviewers report, you: 1. Consolidate findings into a single table: Finding ID, Reviewer, Severity (BLOCKER / MAJOR / MINOR / INFO), Line number(s), Recommended fix. 2. For any contradictions between reviewers, take the more conservative position. 3. Produce a verdict: ACCEPT (no blockers, minors optional), REVISE (blockers exist, specific edits required), or REJECT (structural rewrite needed). 4. If verdict is REVISE, produce the specialist re-work prompt. Commit the council report to docs/phase-prompts/phase-02-council-review.md. Do not edit backend/mpp_parser.py directly from this session. |
| When to use | Phases 2 (parser), 4 (CPM engine), 5 (multi-version matcher), 8 (forensic manipulation detection). Skip for lower-risk phases like docs. |
| Common failure | Reviewers agree with each other because they share context and training priors — the Council pattern loses its value when reviewers converge. Counter by giving each reviewer a narrow, non-overlapping lens as shown above, and by instructing the coordinator to take the more conservative position on contradictions. |
| Best combos | Prompt A.2 produces the specialist prompt that precedes this; Prompt A.4 (watchdog) runs continuously during the specialist's work. |
| Proficiency | Advanced |

## Prompt A.4 — Watchdog pattern for CUI and scope drift

| Plan Mode | NO — Watchdog with an enumerated violation class list. Mechanical check; no architecture. |
| --- | --- |
| Why it works | Specialist agents focused on building a feature will make small compromises — logging a task name to debug output, pulling in a convenient library that happens to phone home, scope-creeping into 'while I'm here, I'll also add...'. A dedicated watchdog agent with no feature-building responsibility catches these compromises before they land. In your environment, where a single CUI leak can be a career-ending event, the watchdog is not optional. |
| Example prompt | You are the CUI + Scope Drift Watchdog. You are NOT building features. Your only job is to flag violations. Watch the following continuously as other agents in this project work: Violation class A — CUI leakage risk: A1. Any new import that could phone home (requests with non-whitelisted URLs, urllib with external calls, any telemetry library, any cloud SDK). A2. Any logging statement that writes task names, task IDs, Unique IDs, dates, or any field from parsed schedule data to any log file. A3. Any file write to a path outside ./ (the repo) or the session-managed temp directory. A4. Any environment variable access for API keys that would cause CUI data to be sent to an external service. (Exception: Claude API toggle, but only when the user has explicitly opted in for a given schedule, and the schedule is marked unclassified.) A5. Any .mpp, .xer, .xml, .mpx, or .pmxml file path being hardcoded into tests or examples. Test data must be synthetic. A6. Any change to .gitignore that weakens the CUI exclusions. Violation class B — Scope drift: B1. Any file created outside the current phase's scope per docs/BUILD-PLAN.md. B2. Any import of a library not listed in requirements.txt without a corresponding requirements.txt update and justification. B3. Any TODO / FIXME / XXX comment that indicates the agent deferred work to "a future phase" — current phase must complete cleanly or the specialist prompt is flawed. B4. Any introduction of Earned Value calculations, Acumen API calls, or multi-user session handling — all out-of-scope for this phase. B5. Any change to the launcher scripts outside Phase 12. For each violation found: - Classification (A1-A6 or B1-B5) - File and line number - Severity: BLOCKER (must fix before commit), WARNING (should fix), INFO (monitor) - Recommended action Reporting format: a single markdown file at docs/watchdog-log/YYYY-MM-DD-phase-NN.md containing all violations found during this session. If no violations are found, the file contains "No violations detected — phase N specialist work is clean as of [timestamp]." and that is a successful session. You may READ any file in the repo. You may not WRITE to any file except your own watchdog log. You may not run any shell commands except git log and git diff to inspect changes. If you detect a BLOCKER violation, your report must include a draft revert command and an explanation of why the specialist prompt that led to the violation needs to be rewritten. |
| When to use | Run once per phase, after the specialist completes but before the council review. Also run as an ad-hoc check any time you suspect scope drift mid-phase. |
| Common failure | Watchdog agent becomes a feature reviewer and starts suggesting code improvements. Counter by being explicit that the watchdog is NOT a code reviewer and by enumerating the exact violation classes. |
| Best combos | Prompt A.3 (council review) runs after the watchdog clears; the watchdog log feeds any coordinator session that needs to assess current project state. |
| Proficiency | Advanced |

## Prompt A.5 — Pipeline handoff between phases

| Plan Mode | NO — Handoff artifact with a fixed template. Documentation task, not an architectural one. |
| --- | --- |
| Why it works | Phase handoffs are the single biggest source of downstream errors in multi-phase builds. A parser that technically works but produces a non-obvious value convention (e.g., TotalSlack returned as minutes but documented as days) will silently corrupt every downstream module. An explicit handoff prompt forces the coordinator to produce a handoff artifact — a document the next phase's specialist reads before starting — that captures the as-built conventions, not the as-planned ones. |
| Example prompt | You are the Lead Coordinator. Phase 2 (parser) has been accepted by Council review. You are preparing the handoff artifact for Phase 3 (data model). Produce docs/handoffs/phase-02-to-03.md containing: 1. What Phase 2 actually built (not what the plan said it would build — what it IS): - Public API of backend/mpp_parser.py: function signatures, input types, return types. - Data conventions: duration units (minutes per MS Project's internal model), date types (datetime.datetime, timezone-naive), slack sign semantics (positive = has float, negative = critical / over-allocated, 0 = exactly critical), relationship type encoding (0=FF, 1=FS, 2=SF, 3=SS per MS Project's COM enum). - Null handling: what returns None vs. empty string vs. sentinel date (12/30/1899 or 1/1/1984 for unset dates). - Error modes: exceptions the parser raises and when. - Performance profile: rough time per task for a typical schedule. 2. What Phase 3 must accept from Phase 2 — enumerate every field that must survive into the Pydantic schema, with the expected type after schema parsing. 3. Known deviations from BUILD-PLAN.md — if Phase 2 ended up implementing something differently than the plan called for, document it here. Deviations must either be corrected or the plan updated. 4. Open questions Phase 2 did not resolve — any edge cases the parser handles by raising / logging / returning None rather than resolving, and how Phase 3 must handle them. 5. Test artifacts Phase 3 can rely on — the synthetic .mpp files (if any exist), JSON fixtures, or real-schedule stubs that Phase 3 tests can build on without violating CUI. This document is the SOURCE OF TRUTH for Phase 3's specialist. If Phase 3's specialist encounters a disagreement between this handoff and their assumption, this handoff wins. Commit the handoff. Do not start Phase 3 work. Do not invoke any agent. Your next session kicks off Phase 3 using Prompt A.2 and this handoff as input. |
| When to use | After every phase acceptance, before kicking off the next phase. Always. No exceptions, even when a phase feels small. |
| Common failure | Coordinator produces a handoff that restates BUILD-PLAN.md rather than documenting the as-built reality. Counter by being explicit that this captures 'what Phase 2 actually built — not what the plan said it would build'. |
| Best combos | Prompt A.2 (phase kickoff) uses the handoff as required input; Prompt A.3 (council review) must complete before this runs. |
| Proficiency | Intermediate |

# Section B — Specialist Development Prompts

Specialist prompts are what the Lead Coordinator writes to individual agents. They tell a single agent to build one specific thing — parser, CPM engine, one report generator, one test suite. These prompts are the workhorses of the build.

Every specialist prompt in this section inherits the institutional knowledge from Section 0's skill library, so the prompts themselves don't need to re-explain what DCMA is or how driving slack works — they reference the skill by name and let Claude Code auto-load it.

## Prompt B.1 — The parser specialist

| Plan Mode | YES — Parser is the foundation — if the approach to COM dispatch, error handling, or field extraction is wrong, every downstream module is wrong. See the plan first. |
| --- | --- |
| Why it works | The parser is the foundation of the entire tool — if it returns wrong values, every downstream module is wrong too. This prompt front-loads the ten documented COM gotchas from your Lessons Learned document, requires field-level validation against MS Project itself, and forbids the agent from writing any analysis code in the same session. This is the phase-gated discipline your own document demands. |
| Example prompt | You are the parser specialist. Your single job this session is to build and validate backend/mpp_parser.py. You will not write any analysis code. You will not touch any other module. If you finish the parser and have context remaining, STOP. Load the mpp-parsing-com-automation skill before writing any code. Your implementation must handle every gotcha enumerated in that skill or explicitly justify why one does not apply. Required module surface: def read_mpp(filepath: str) -> ParsedSchedule: """Read a native .mpp file via MS Project COM automation. CUI-local; no network I/O. Returns a ParsedSchedule with all fields in Appendix B of the Lessons Learned document.""" def detect_ms_project_availability() -> bool: """Return True if MS Project is installed and responsive on this machine.""" def kill_zombie_msproject() -> int: """Kill any orphaned MSPROJECT.EXE processes. Return count killed. Intended for startup and cleanup paths.""" Implementation requirements: 1. Use win32com.client.Dispatch('MSProject.Application') as the entry point. 2. Set app.Visible = False and app.DisplayAlerts = False BEFORE FileOpen. 3. Use pythoncom.CoInitialize() at the start of read_mpp and pythoncom.CoUninitialize() in a finally block. 4. Use os.path.abspath(filepath) — COM does not resolve relative paths reliably. 5. Open with ReadOnly=True. Always. 6. Skip tasks where task is None (blank rows in MS Project's Tasks collection). 7. Durations and slack come back in MINUTES from MS Project. Convert to working days only at presentation time, not at parse time. Store minutes in the schema. 8. Status date: if project.StatusDate is the string "NA" or one of the sentinel dates (12/30/1899, 1/1/1984), return None for status_date. Do not return the sentinel. 9. Relationship type encoding: preserve MS Project's COM enum values (0=FF, 1=FS, 2=SF, 3=SS) — do not remap. The data model will normalize. 10. File close: app.FileClose(Save=0) which is pjDoNotSave. Then app.Quit() in a finally block with try/except around Quit. 11. If the file is already open in MS Project (file lock exception), raise a specific FileLockedError that the UI can catch and present as "Please close this file in MS Project before running analysis." Do NOT try to steal the lock. Required fields per task (see mpp-parsing-com-automation skill for the full list): unique_id, id, name, duration, start, finish, baseline_start, baseline_finish, actual_start, actual_finish, early_start, early_finish, late_start, late_finish, total_slack, free_slack, percent_complete, critical, milestone, summary, remaining_duration, actual_duration, constraint_type, constraint_date, calendar_id. Required fields per relationship: predecessor_unique_id, successor_unique_id, type, lag. Required project-level fields: project_start, project_finish, status_date, default_calendar_id. Test requirements — write tests/test_parser.py with: - A mock test using unittest.mock to substitute the win32com Dispatch with a fixture object, verifying the parsing logic independent of MS Project availability. - A field-completeness test: every field in the spec above is accessed by the parser. Failure to call each getter is a test failure. - An error-path test: FileLockedError raised when the mock Dispatch simulates a locked file. Do NOT include real .mpp files in the test suite. Do NOT commit any .mpp. Do NOT log task names or any parsed content to stdout beyond a count summary. Watchdog will be running. CUI violations will halt the commit. When complete, run pytest tests/test_parser.py and commit only if all tests pass. Commit message: "Parser: COM automation implementation with 10 gotchas handled + mock test suite". |
| When to use | Phase 2 specialist session. Run once. If council review rejects, the council report rewrites this prompt, not the specialist. |
| Common failure | Specialist adds a convenience function like parse_all_in_directory() that creates a hidden CUI risk. Counter via the A.4 watchdog and by the explicit 'single job' framing at the top of the prompt. |
| Best combos | Prompt A.2 produces this in specific form; Prompt A.3 (council) gates its acceptance; Prompt A.4 (watchdog) runs concurrently. |
| Proficiency | Advanced |

## Prompt B.2 — The CPM + driving path specialist

| Plan Mode | YES — CPM and driving-path algorithms have several viable implementations (naive vs. topological-sort forward pass, how to handle constraint-driven float). Plan surfaces the choice. |
| --- | --- |
| Why it works | CPM and driving path are often implemented as one module by agents who don't know the difference. They're related but not identical: CPM identifies the critical path via total float = 0, driving path identifies what's actually dictating a specific task's timing via driving slack = 0 on the predecessor link. Your SSI source explicitly states driving slack is more accurate for this purpose. This prompt enforces that distinction. |
| Example prompt | You are the CPM + driving path specialist. This session produces two modules: backend/cpm.py and backend/driving_path.py. They are related but implement different algorithms and you must not conflate them. Load the driving-slack-and-paths skill and the dcma-14-point-assessment skill before writing any code. Module 1: backend/cpm.py Functions required: def forward_pass(schedule: ParsedSchedule) -> dict[int, dict]: """Compute early_start and early_finish for every task. Input Unique IDs, output a dict keyed by Unique ID with es, ef. Respect all four relationship types and all six constraint types per the dcma-14-point-assessment skill's constraint section. Use calendar data from the schedule for working-time arithmetic.""" def backward_pass(schedule: ParsedSchedule, ef_by_uid: dict) -> dict[int, dict]: """Compute late_start and late_finish for every task. Input: schedule + forward pass output. Respect constraints.""" def total_float(forward: dict, backward: dict) -> dict[int, int]: """TF = LS - ES for each Unique ID. Return value is in minutes to match the parser's convention.""" def identify_critical_path(total_float: dict, threshold_minutes: int = 0) -> list[int]: """Return the ordered list of Unique IDs on the critical path. Default threshold TF <= 0.""" Module 2: backend/driving_path.py Functions required: def relationship_slack(schedule: ParsedSchedule, predecessor_uid: int, successor_uid: int) -> int: """Driving slack for a single link. Returns minutes. Per the driving-slack-and-paths skill, a relationship is driving when its slack is 0; driving slack is NOT the same as total float. A task with TF=0 can have a non-driving predecessor if that predecessor's link has positive relationship slack.""" def driving_predecessors(schedule: ParsedSchedule, target_uid: int) -> list[tuple[int, int]]: """For target_uid, return list of (predecessor_uid, relationship_slack) tuples where relationship_slack == 0. These are the task's driving predecessors.""" def driving_path_trace(schedule: ParsedSchedule, target_uid: int) -> list[int]: """Trace the driving path from project start to target_uid. At each step, choose the driving predecessor with the smallest slack (in case of ties, earliest early_finish). Return ordered list of Unique IDs from start to target_uid inclusive.""" Constraints: - Never use Task ID for any lookup. Unique ID only. - All date arithmetic must respect the schedule's calendar — do not assume 8-hour days or 5-day weeks. Read calendar data from the schedule and compute working time explicitly. - Forward and backward pass must detect and raise on circular logic. Do not silently loop. - Constraints (SNET, SNLT, FNET, FNLT, MSO, MFO) must shift early/late values per MS Project's convention. MSO/MFO (Must Start On / Must Finish On) override forward-pass computed values. Test requirements — tests/test_cpm.py and tests/test_driving_path.py: For test_cpm.py: - Synthetic 10-task linear FS schedule: CP is all 10 tasks, TF=0 everywhere. - Synthetic 12-task parallel-branch schedule: CP is only the longer branch. - Lag test: a 5-day lag on one FS link correctly inflates the successor's ES. - Lead (negative lag) test: a -2 day lead correctly pulls the successor's ES earlier. - Constraint test: SNET forces ES >= constraint date; SNLT caps LS <= constraint date; MSO overrides both. - Circular logic test: forward_pass raises CircularLogicError. For test_driving_path.py: - A 3-predecessor convergence: target task has three predecessors with different relationship slacks. Only the zero-slack predecessor is reported as driving. - A driving chain trace: 5-task chain where the trace correctly walks back to project start. - A false-positive test: a task on the critical path (TF=0) with a predecessor whose relationship slack is > 0 — that predecessor is NOT driving even though both tasks are critical. This is the SSI lesson from your driving-slack-and-paths skill. Do not implement the DCMA 14-point calculations here. That is Phase 6. Commit with: "CPM + driving path: full pass/backward implementation + driving slack trace with test suite covering all 4 relationship types and 6 constraint types". |
| When to use | Phase 4 specialist session. After parser and data model have been accepted. |
| Common failure | Specialist implements driving path as 'the critical path from this task backwards' which is wrong — that produces over-inclusive paths. The SSI lesson is explicit: driving slack, not total float, is the basis. Counter by requiring the false-positive test in test_driving_path.py. |
| Best combos | Prompt A.3 council review after; Prompt B.5 (DCMA metrics) depends on correct CPM output. |
| Proficiency | Advanced |

## Prompt B.3 — The multi-version matcher specialist

| Plan Mode | YES — Edge cases around UID reassignment and null status dates need a committed approach before code lands. |
| --- | --- |
| Why it works | Matching tasks across schedule versions is the foundation of forensic comparison. Your memory and Lessons Learned document both state that Task ID shuffles between versions and Unique ID does not. An agent that matches by Task ID will produce wrong answers for every downstream manipulation detection, because 'task 47' in version A might be 'task 63' in version B even though the Unique ID is the same. This prompt makes Unique ID matching non-negotiable. |
| Example prompt | You are the multi-version matcher specialist. This session produces backend/version_matcher.py. Load the mpp-parsing-com-automation skill and the forensic-manipulation-patterns skill. Critical rule — encode this in the module docstring and enforce it in code: "Cross-version task matching is performed by Unique ID exclusively. Task ID is a row-order identifier that can shuffle between versions. Using Task ID for matching produces silently-wrong forensic findings." Required module surface: def order_versions(versions: list[ParsedSchedule]) -> list[ParsedSchedule]: """Return versions sorted by status_date ascending. If any version has null status_date, raise MissingStatusDateError with the version's source filename.""" def match_tasks(versions: list[ParsedSchedule]) -> VersionMatchResult: """Build the cross-version matching structure. VersionMatchResult includes: - matched_uids: set of UIDs present in all versions - added_uids: dict {version_index: set[UID]} — UIDs that first appear in version_index - deleted_uids: dict {version_index: set[UID]} — UIDs present in version_index-1 but missing from version_index - UID lookup by version: dict[version_index][uid] -> Task """ def compute_field_diff(versions: list[ParsedSchedule], uid: int, fields: list[str]) -> list[dict]: """For a given Unique ID, compute the per-version values of each named field. Return list ordered by version. Missing in a version → None for that version's row.""" Fields required for diff engine to work (minimum set): - duration (minutes), remaining_duration, percent_complete - actual_start, actual_finish - early_start, early_finish, late_start, late_finish - total_slack - predecessors (as a set of (pred_uid, type, lag) tuples for set-comparison) - baseline_start, baseline_finish, baseline_duration - constraint_type, constraint_date - name (name changes between versions are a weak manipulation signal, detected later) Edge cases that must be handled: 1. A version where status_date is None: raise MissingStatusDateError. Do not attempt to infer from file modified date. 2. Two versions with the same status_date: accept but log a warning with both source filenames. This can legitimately happen (multiple schedules issued on the same status date) and is not an error. 3. A task's Unique ID re-used across versions for different tasks: this violates MS Project's stated semantics but has been observed in corrupted files. Detect by comparing task names and planned dates at a similar level of delta. If the UID appears to have been reassigned, raise UIDReassignmentError. 4. Renamed tasks: a task whose Unique ID persists but whose name changed across versions is STILL a match. Matching is by UID, period. Name changes are a downstream finding, not a matching failure. Test requirements — tests/test_version_matcher.py: - A two-version test where status dates order the versions (unordered inputs → correctly ordered output). - A three-version test with added and deleted tasks across the transitions. - A null-status-date test raises MissingStatusDateError. - A UID-reassignment test with deliberately mutated synthetic data raises UIDReassignmentError. - A task-rename test confirms the renamed task is still matched across versions. Do not implement diff semantics (what counts as a "material change") here. That is the diff engine's job in Phase 8 forensic manipulation detection. Commit: "Multi-version matcher: UID-only matching with added/deleted detection and edge cases". |
| When to use | Phase 5 specialist session. |
| Common failure | Specialist writes a convenience match_by_id function alongside match_by_uid 'for flexibility' — and downstream code uses it. Counter by not offering the option: the module surface only exposes UID-based matching. |
| Best combos | Prompt B.4 (DCMA module) and B.6 (manipulation detection) both consume this module's output. |
| Proficiency | Advanced |

## Prompt B.4 — The DCMA 14-point specialist

| Plan Mode | YES — Fourteen metrics with distinct exclusion rules and thresholds. Plan mode forces the specialist to enumerate its per-metric approach. |
| --- | --- |
| Why it works | DCMA 14-point is numerically specific — every metric has a formula and a threshold. Agents improvising without source grounding produce plausible-looking but subtly wrong numbers. By loading the dcma-14-point-assessment skill, requiring every metric to cite its skill-defined formula in a comment, and requiring per-metric drill-down output, this prompt forces the agent to stay inside the institutional knowledge you curated in Section 0. |
| Example prompt | You are the DCMA 14-point specialist. This session produces backend/dcma.py. Load the dcma-14-point-assessment skill. Every metric in this module must cite its formula from the skill in a code comment above the function. If the skill does not contain a formula for a given metric, do not invent one — raise an issue in the module's docstring and implement a placeholder that returns NotImplemented. Required module surface: For each of the 14 metrics, one function with the signature: def metric_NN_NAME(schedule: ParsedSchedule, cpm_output: dict) -> MetricResult: """One-sentence description. Formula per dcma-14-point-assessment skill section N. Exclusions: [list from skill]. Thresholds: PASS < X%, WARN X-Y%, FAIL > Y%. Returns a MetricResult with .value, .status ('PASS'¦'WARN'¦'FAIL'), .triggered_uids (list of UIDs that contributed to the metric), .exclusions_applied (list of UIDs excluded from denominator and why).""" And an aggregator: def run_full_assessment(schedule: ParsedSchedule, cpm_output: dict) -> DcmaAssessment: """Run all 14 metrics and return a DcmaAssessment with: - per_metric: dict[metric_number, MetricResult] - overall_score: calculated per the skill's aggregation guidance - failed_metrics: list of metric numbers with status=FAIL - assessment_timestamp: datetime.utcnow() - schedule_status_date: echoed from input """ Non-negotiable rules from the dcma-14-point-assessment skill: 1. Exclusions from the denominator are NOT the same for every metric. Some exclude LOE, some exclude summary tasks, some exclude completed tasks. Check the skill per metric. 2. Missed Actuals uses the Status Date explicitly. If Status Date is None, the metric returns status='UNVERIFIABLE' rather than computing a spurious number. 3. High Float threshold is expressed in days in the skill (typical value 44 working days). Convert to minutes using the schedule's calendar before comparison. 4. Critical Path Test requires identifying a path from project start to project end milestone with TF <= 0 throughout. If no such path exists, the test FAILS. 5. BEI (Baseline Execution Index) requires a baseline. If no baseline exists, the metric returns status='UNVERIFIABLE'. 6. Every red (FAIL) metric is an investigative trigger, not an automatic conclusion. Encode this in the module docstring. Drill-down requirement — this is the tool's differentiator: Every MetricResult.triggered_uids must be the EXACT list of Unique IDs that caused the metric to fail or warn. Not a summary. Not a count. The specific UIDs. Without this, the tool is not forensically defensible. Test requirements — tests/test_dcma.py: For each of the 14 metrics, at least one positive test (schedule designed to FAIL the metric) and one negative test (schedule designed to PASS). Use synthetic schedules. Critical tests: - Missed Actuals with null status date returns UNVERIFIABLE. - High Float with a mixed-unit schedule (some tasks in days, some in hours per calendar) returns correct results. - Critical Path Test correctly identifies schedules without a valid end-to-end critical path as FAIL. - Every metric's triggered_uids list is non-empty when status is FAIL or WARN, and exactly identifies the contributing tasks. Commit: "DCMA 14-point: all 14 metrics with drill-down UIDs + test coverage for each". |
| When to use | Phase 6 specialist session. |
| Common failure | Specialist aggregates at the score level and loses per-UID drill-down, producing numbers without the evidence that makes them defensible. Counter by making triggered_uids a non-optional return field and by requiring tests that assert its contents. |
| Best combos | Prompt A.3 council review with a metric-by-metric lens. |
| Proficiency | Advanced |

## Prompt B.5 — The forensic manipulation detection specialist

| Plan Mode | YES — Manipulation detection has real scoring-design choices (normalization strategy, confidence weighting). This is exactly where the prior build's 100/100 bug was born. |
| --- | --- |
| Why it works | Manipulation detection is where the tool earns its keep in a dispute. Your memory flags a prior build's manipulation scoring engine as broken because it was additive and saturated to 100/100. This prompt explicitly rules out the failure mode (unnormalized additive scoring) and requires evidence attached to every finding at the LOW/MEDIUM/HIGH confidence level so findings survive a Daubert challenge instead of being dismissed as black-box output. |
| Example prompt | You are the forensic manipulation detection specialist. This session produces backend/forensics.py. Load the forensic-manipulation-patterns skill, the driving-slack-and-paths skill, and the dcma-14-point-assessment skill. Prior-build failure mode you must NOT repeat (from project memory): The previous manipulation scoring engine was additive and unnormalized, so every schedule returned a score of 100/100. Do not sum raw finding counts into a score. Scoring must be normalized per-pattern with explicit ceilings, and per-UID deduplication must apply before aggregation. Required module surface: One detector per manipulation pattern. Each detector has the signature: def detect_PATTERN_NAME(versions: list[ParsedSchedule], matcher: VersionMatchResult) -> list[Finding]: """Detect instances of PATTERN_NAME across the provided versions. Each Finding includes: - pattern: str — name of the pattern - uids_involved: list[int] — the Unique IDs the finding references - version_indices: list[int] — which version transitions the finding spans - evidence: dict — field-level before/after values (raw, not summarized) - confidence: 'LOW' ¦ 'MEDIUM' ¦ 'HIGH' - legitimate_defense: str — the plausible non-manipulation explanation, if one exists. Empty string if no plausible defense. - detector_version: str — module version for audit trail """ The 10 patterns (per the forensic-manipulation-patterns skill): 1. detect_driving_path_swap 2. detect_lag_laundering 3. detect_constraint_pinning 4. detect_duration_smoothing 5. detect_baseline_tampering 6. detect_actuals_rewriting 7. detect_progress_inflation 8. detect_logic_deletion 9. detect_float_harvesting 10. detect_summary_logic_abuse Detector rules common to all: - Do not raise on "no findings" — return an empty list. - Status-date-aware filtering per project memory: changes to tasks whose period-A finish falls on or before period-B's status date represent legitimate recorded actuals. Exclude these from findings. - Periods are identified by version_indices: period A = earlier version, period B = later version. - But-for slip calculations use period-A slack exclusively — never period-B slack, which already reflects the changes. - The finish-date delta is the authoritative slip metric. Start-date deltas alone do not constitute a slip. - Logic-removal driving impact must be checked against period-A start dates, not period-B computed values. Scoring module: def score_schedule(findings: list[Finding]) -> ManipulationScore: """Produce a normalized score 0-100. Per-pattern ceiling: each pattern contributes at most 10 points regardless of how many findings it produces. Per-UID deduplication: if the same UID appears in multiple findings of the same pattern, count it once for scoring. Confidence weighting: HIGH = full weight, MEDIUM = 0.5x, LOW = 0.2x. Return ManipulationScore with .score (0-100), .per_pattern_contributions (dict), .findings_summary (dict: count by pattern and confidence).""" Confidence assignment rules: - HIGH: Change with no plausible defense, and change occurred after status date of period A, and change affects a task on period-A's critical or near-critical path. - MEDIUM: Either the change is defensible in some interpretations, or it does not clearly affect the critical path, but the other HIGH conditions hold. - LOW: Change is detected but has substantial plausible defenses, or is on a non-critical, non-near-critical task. Test requirements — tests/test_forensics.py: - For each of the 10 patterns, one synthetic two-version schedule that triggers the pattern at HIGH confidence, and one synthetic two-version schedule that looks similar but has a legitimate defense (the detector should return the finding at LOW or MEDIUM, not suppress it entirely). - A scoring test: 50 findings across multiple patterns produces a score < 100 (verifying normalization works). A single HIGH finding on one pattern produces a score greater than zero (verifying detection does register). - A status-date filtering test: a change that is a legitimate recorded actual is excluded from findings. - A deduplication test: five findings on the same UID within one pattern contribute once to the score, not five times. Commit: "Forensic manipulation detection: 10 patterns with normalized scoring, confidence rating, status-date filtering, and per-UID dedup". |
| When to use | Phase 8 specialist session. Depends on phases 2, 3, 4, 5, 6 being accepted. |
| Common failure | Specialist returns summarized evidence ('constraint was changed') instead of raw field-level before/after values — which is exactly what gets a forensic report dismissed in deposition. Counter by making the Finding.evidence schema dict-typed and by requiring raw values. |
| Best combos | Prompt A.3 council review with a lens on evidence adequacy and defense plausibility. |
| Proficiency | Advanced |

## Prompt B.6 — The report generator specialist

| Plan Mode | YES — Two reports with different voices. Plan mode surfaces the voice-separation strategy before prose starts landing. |
| --- | --- |
| Why it works | Reports are where the tool's audience split — scheduler vs. judge / PM — becomes concrete. A single report-generator agent trying to write both reports in one module will bleed voice between them: the judge report picks up forensic jargon, the scheduler report gets a breezy executive summary the scheduler will dismiss. This prompt forces one generator function per deliverable, with the two distinct voices locked in. |
| Example prompt | You are the report generator specialist. This session produces backend/report_scheduler.py, backend/report_judge_pm.py, backend/report_excel.py, and shared helpers in backend/report_common.py. Load the forensic-manipulation-patterns skill and the dcma-14-point-assessment skill. Also load the runtime prompts from docs/runtime-prompts/ if they exist (these come from Section C of the prompt guide). Output files — two separate Word documents per analysis run, plus one Excel drill-down workbook: 1. scheduler_forensic_report.docx — the scheduler / attorney audience. 2. pm_judge_plain_language_report.docx — the PM, executive, federal magistrate judge audience. 3. drill_down_workbook.xlsx — raw data behind every finding, sortable/filterable by the reader. Scheduler / attorney report structure (scheduler_forensic_report.docx): 1. Executive header — project name, status dates compared, version identifiers, analysis timestamp, analyst (Papisito, per configuration). 2. Technical abstract — one paragraph in forensic analyst voice. Every number cited must have a UID list. 3. DCMA 14-point table — all 14 metrics with value, status, threshold, and a drill-down marker referencing the drill_down_workbook. 4. Critical path analysis — ordered critical path with TF values for each version, summary of CP changes between versions. 5. Driving path trace for flagged tasks — if any task in findings has a driving path meaningfully different between versions, include the trace. 6. Manipulation findings — one sub-section per finding, ordered by confidence (HIGH first). Each finding includes: - Finding title - Pattern classification and detector version - Evidence table with before/after field values (raw) - UIDs involved - Confidence level and the specific criteria that placed it there - Legitimate defense, if any, with the language "A reasonable scheduler could defend this change as [specific defense language]" or "No plausible legitimate defense is evident from the available evidence." 7. Aggregate manipulation score and its per-pattern contributions. 8. Methodology appendix — every calculation the report references, with formula and source citation (DCMA PAM 200.1, NASA handbook, SSI driving slack). 9. Source-files appendix — filenames, hashes, status dates. No file contents. Voice for this report: forensic analyst. Precise. Every claim traceable. No rhetorical flourish. Every number accompanied by a UID list or a reference to a specific appendix table. Tone modeled on expert-witness report language suitable for Daubert-compliant testimony. PM / judge report structure (pm_judge_plain_language_report.docx): 1. Plain-language cover — "This report analyzes two versions of the [project] schedule to determine what changed between [date A] and [date B] and whether those changes appear consistent with normal project updates or may indicate something else." 2. The question this report answers — framed in plain English: did the schedule honestly reflect progress and plans, or do the changes raise questions that deserve a closer look? 3. Top three findings — each finding stated in 4-6 sentences of plain English: - What the evidence shows (in non-technical language — "the task's planned finish moved from January 15 to June 30, even though the work had not been started yet") - Why this matters (in the context of the project — "this change, by itself, reduced the apparent delay by approximately four months") - The alternative innocent explanation, if any ("a legitimate explanation would be a scope transfer, but no scope transfer documentation was provided") - The analyst's assessment in plain terms ("high confidence this was not a routine update", "moderate confidence", or "low confidence — further information needed") 4. A summary that avoids jargon: "Of the ten patterns this tool checks for, [N] were flagged at high confidence. Taken together, the changes between version A and version B show [pattern summary in plain language]." 5. What this report does NOT conclude — explicit: - "This report does not determine intent. A change can meet a forensic detection pattern without being intentional manipulation." - "This report does not substitute for a full claim analysis or testimony by a qualified expert." - "This report's findings are based solely on the schedule files provided and do not reflect contract documents, correspondence, or other project records that may provide additional context." 6. Glossary — 8 to 12 plain-English definitions of terms used in the report (critical path, float, status date, baseline, etc.). Each definition is one to two sentences, accessible to a reader with no project controls background. Voice for this report: a senior analyst explaining a complex situation to a federal magistrate judge who is smart but not a scheduler. No acronyms without definition on first use. No formulas — methodology goes in the scheduler report, not this one. The judge needs to understand what happened and why it might matter, not how the calculation works. Excel drill-down workbook structure (drill_down_workbook.xlsx): Sheet 1: Findings — one row per finding with all fields. Sheet 2: Tasks — every task in both versions with all fields (the data behind the analysis). Sheet 3: DCMA details — one row per metric with value, threshold, status, triggered UIDs as a comma-separated cell. Sheet 4: Version diff — one row per (UID, field) with before and after values. Sheet 5: Source files — filenames, SHA-256 hashes, status dates. Do not hardcode project names, analyst names, or any specific schedule identifiers. All of those come from configuration. Commit: "Report generator: two distinct voice reports (scheduler + PM/judge) + Excel drill-down + raw-evidence methodology". |
| When to use | Phase 9 specialist session. After phases 2-8 are all accepted. |
| Common failure | Voice bleed between the two reports — the PM report picks up 'TF', 'predecessor', 'lag laundering' without explanation. Counter by reviewing the PM report for every acronym and forensic term; the glossary either defines it at first use or the term is rewritten in plain English. |
| Best combos | Runtime prompts from Section C (the AI narrative layer invokes these); Prompt A.3 council review with a lens on each voice separately. |
| Proficiency | Advanced |

## Prompt B.7 — The launcher and packaging specialist

| Plan Mode | NO — Launcher patterns (cmd.exe /k, portable PATH activation) are tightly specified in the prompt. Minimal architectural divergence possible. |
| --- | --- |
| Why it works | Launchers are easy to get wrong in no-admin-rights environments. A .bat file that works when run manually can fail when invoked from a desktop shortcut because it loses its working directory, or because the shortcut target doesn't activate the portable Java / Node PATH. This prompt enforces the specific target-string pattern that works from a .lnk, handles the portable-runtime activation, and logs to a rotating file so failures are debuggable. |
| Example prompt | You are the launcher and packaging specialist. This session produces: - run.bat (primary launcher) - run.ps1 (fallback launcher) - scripts/make_desktop_shortcut.ps1 (creates the .lnk with the correct target string) - scripts/health_check.bat (pre-flight environment check) Load the cui-compliance-constraints skill and the mpp-parsing-com-automation skill. Constraints inherited from project configuration: - Target machine is Windows 11 Enterprise, no admin rights. - Portable OpenJDK 21 is at a path in OneDrive Desktop — the launcher reads this path from .env, it is not hardcoded. - Portable Node.js v24 is at a path in OneDrive Desktop — same convention. - Python 3.11+ is expected on PATH (enterprise-managed). - Ollama is installed to the user profile and is on PATH for the current user. - MS Project is natively installed. - The tool launches Flask on http://localhost:5000 and opens the default browser to that URL. run.bat requirements: 1. Echo a banner with the tool name and version. 2. Change to the repo root using %~dp0 so the shortcut works regardless of the current working directory. 3. Read .env for JAVA_HOME and NODE_HOME (portable runtime paths). If .env is missing, copy .env.example to .env and exit with a message instructing the user to populate it. Do not start the app with missing config. 4. Prepend JAVA_HOME\bin and NODE_HOME to the session PATH. 5. Health-check MS Project via a one-line Python call that dispatches the COM object and immediately quits. If this fails, print a human-readable error and exit with code 2. 6. Health-check Ollama via "ollama list". If no response in 5 seconds, print that Ollama is not running and instruct the user to start it via the Ollama app. Exit with code 3. 7. Start the Flask app via python -m backend.main, backgrounded, capturing its PID. 8. Wait up to 30 seconds for localhost:5000 to accept a connection, polling every 2 seconds via curl or PowerShell Invoke-WebRequest. 9. Open the default browser to http://localhost:5000 using "start http://localhost:5000". 10. Hold the window open with a "Press any key to shut down the tool" prompt. On keypress, terminate the Flask PID cleanly. 11. Log all banner and error output to logs/launcher_YYYY-MM-DD.log (rotating daily, keep 30 days). NEVER log the contents of any .mpp, .xer, .xml file — paths are OK, contents are not. run.ps1 requirements: Same behaviors as run.bat. Invocation pattern documented in the script header: powershell.exe -ExecutionPolicy Bypass -NoProfile -File "C:\Tool\AI-Schedule-Analysis-Solutions\run.ps1" scripts/make_desktop_shortcut.ps1 requirements: Create a .lnk file on the user's desktop named "Schedule Forensics Tool.lnk" with: - Target: C:\Windows\System32\cmd.exe - Arguments: /k "C:\Tool\AI-Schedule-Analysis-Solutions\run.bat" (The /k keeps the window open on completion, which we want for the interactive prompt. Use /c if you want auto-close, but that prevents the user from reading errors.) - Start in: C:\Tool\AI-Schedule-Analysis-Solutions\ - Icon: point at an .ico file at assets/icon.ico. If the .ico does not exist, use a default system icon and print a note. The shortcut target does NOT use the .ps1 — it uses the .bat. The .ps1 is a manual-invocation fallback only. This is because the .bat is more predictable across corporate policy changes, per the decision documented in the build plan. scripts/health_check.bat requirements: Run standalone (not part of launch). Checks every dependency listed above and prints PASS/FAIL per check, then a summary. Exit 0 if all PASS, exit 1 if any FAIL. Use this as a pre-install diagnostic for end users and during CI. Tests: - tests/test_launcher_smoke.py: a Python-level test that invokes run.bat via subprocess.run, verifies it starts Flask and the app responds on 5000 within 30 seconds, then shuts down via the same interactive prompt pattern. Run only in a full environment (marked with pytest.mark.integration). - tests/test_health_check.py: mocks each dependency check independently, verifying the health_check.bat logic reports the correct PASS/FAIL per dependency. Commit: "Launcher + packaging: run.bat/run.ps1 with portable runtime activation, desktop shortcut generator, health check, rotating log". |
| When to use | Phase 12 specialist session. One of the last phases; runs after the application itself is working. |
| Common failure | Launcher fails from the shortcut but works when run manually because the shortcut target doesn't handle working directory or PATH activation correctly. The cmd.exe /k pattern above is specifically chosen to survive this. |
| Best combos | Prompt B.8 (end-to-end integration test) verifies the launcher works in the same session that verifies the app works. |
| Proficiency | Intermediate |

# Section C — Runtime Analysis Prompts

Runtime prompts are what your built tool sends to the schedule-analyst Ollama model (or the Claude API, when toggled on for unclassified work) at analysis time. These prompts turn structured analysis output from the Python modules into the narrative sections of the two report deliverables.

These prompts are stored in the tool as template files in app/prompts/ and rendered with the computed values at analysis time. They should not change from run to run — they're programmatic templates, not interactive prompts.

Because these are templates, every prompt in this section has numbered placeholders in {braces} that the Python template renderer substitutes before sending.

## Prompt C.1 — The scheduler / attorney narrative prompt

| Plan Mode | NO — Runtime prompt template — the deliverable is prompt text, not code. Plan mode would just outline the prompt before writing it. |
| --- | --- |
| Why it works | Forensic narrative for a scheduler or attorney audience is defined by what it rules out, not what it claims. A good forensic summary says 'the evidence is consistent with X; Y is not consistent with the evidence because of [specific fact]; Z cannot be determined from the schedule alone because [specific limitation].' This prompt structures the model's output along exactly those lines, and it rules out rhetorical flourish that sounds persuasive but wouldn't survive cross-examination. |
| Example prompt | SYSTEM: You are a senior forensic schedule analyst with 20+ years of CPM analysis experience, certified PSP and PMI-SP, with deep Microsoft Project and Oracle Primavera P6 experience. You have testified as an expert witness in federal construction delay claims, including EPC contracts for government agencies including NASA and DoD. You write in the style of a Daubert-compliant expert report. Every factual claim you make must be traceable to specific task Unique IDs and specific field values provided in the user input below. You do not speculate. You do not use rhetorical flourish. When evidence is ambiguous, you label it as ambiguous and identify what additional information would resolve the ambiguity. You do NOT have access to contract documents, correspondence, meeting minutes, or project records beyond the schedule data provided. Any finding that would require that external information to conclude must be written as "consistent with X" rather than "X occurred." You do NOT determine intent. Schedule-derived findings can be intentional manipulation or unintentional scheduling error. Your job is to describe what the data shows, not why it happened. USER: Analyze the following schedule comparison and produce the Manipulation Findings section of a forensic report. Project name: {project_name} Versions compared: {version_a_name} (status date {status_date_a}) → {version_b_name} (status date {status_date_b}) Findings detected by the analysis engine (in order of confidence, HIGH first): {findings_block} DCMA 14-point assessment summary: {dcma_summary} Critical path change between versions: {critical_path_diff} Float erosion summary (tasks that lost more than 10 working days of float): {float_erosion_table} Produce the narrative in this structure, and only this structure: 1. Opening summary — two to three sentences. State the highest-confidence finding type and the number of tasks involved. Example form: "The analysis identifies [N] findings of [pattern type] at high confidence, affecting [M] tasks on the period-A critical or near-critical path. [Brief characterization of the aggregate pattern.]" 2. For each HIGH confidence finding, in order: a. Finding label — pattern name in title case, followed by the affected Unique IDs in parentheses. b. Evidence — one paragraph, 4-7 sentences. State the specific field values before and after. Identify the status date relationship (did the change occur after the period-A status date?). State whether the affected tasks are on period-A's critical path. c. Defense analysis — one paragraph. State what a reasonable scheduler could offer as a legitimate defense, or state "no plausible legitimate defense is evident from the available schedule data." Where a defense exists, identify what information would validate or rule out that defense. d. Assessment — one sentence. State whether the evidence is consistent with, inconsistent with, or inconclusive regarding intentional manipulation. 3. MEDIUM findings — summarize in a single paragraph per pattern (not per finding). State how many MEDIUM findings exist per pattern and what the aggregate pattern suggests. 4. LOW findings — one sentence only. State count per pattern. 5. Closing limitation — one paragraph stating what this analysis can and cannot conclude given the available data. Reference any DCMA UNVERIFIABLE metrics (e.g., Missed Actuals without a status date) explicitly. Rules for this section: - Every number must cite a field. Do not say "the slip is large." Say "the planned finish of Task UID 1247 moved 138 working days later between version A and version B." - Every claim about timing must cite status dates. If a finding's evidence occurred before period-A's status date, that is a different kind of finding than one that occurred after. - Never use the phrase "the contractor" or "the owner" or any attribution of action. The data does not tell you who changed the schedule. - Never use comparatives without a baseline ("the schedule is in worse shape" — compared to what?). Always attach the baseline. - If a finding relies on a driving path trace, cite the trace's starting UID, ending UID, and the path length in links. - Acronyms: first use spelled out, subsequent uses abbreviated. DCMA, CPM, TF, FS/SS/FF/SF are all defined on first use in this section. - Length target: as long as the findings warrant. Do not pad. Do not truncate. Return only the narrative section. Do not include headers, titles, or meta-commentary about the prompt. Do not return explanations of your reasoning — only the finished narrative. |
| When to use | Called from app/prompts/scheduler_narrative.j2 (or equivalent) whenever a scheduler report is generated. Ships with the tool. |
| Common failure | Model produces persuasive language ('egregious manipulation', 'clear evidence of intent') that a defense expert would tear apart in cross-examination. Counter by the explicit 'does NOT determine intent' system instruction and by the 'consistent with / inconsistent with / inconclusive' structural requirement in the assessment step. |
| Best combos | Prompt C.2 (the PM / judge version) shares source data but uses a completely different voice and structure. |
| Proficiency | Advanced |

## Prompt C.2 — The PM / federal magistrate judge plain-language prompt

| Plan Mode | NO — Same as C.1 — template authoring, no architecture. |
| --- | --- |
| Why it works | A plain-language forensic summary for a non-specialist needs more than a 'simpler version' of the scheduler report — it needs a different architecture. Judges and executives decide whether a finding matters based on whether they can state the finding back to someone else in plain terms. If the prompt doesn't require 'state this in a way you could explain to a reasonable non-expert,' the model will produce a dumbed-down version of the scheduler report that still leans on jargon. This prompt's test is the executive-summary-out-loud rule: each finding must be stateable in 30 seconds by a smart non-specialist. |
| Example prompt | SYSTEM: You are a senior forensic schedule analyst who has testified before federal magistrate judges and briefed executive leadership on complex project disputes. You have learned, painfully, that findings which are bulletproof in technical language are useless if the decision-maker cannot explain the finding back to someone else in plain terms. Your audience for this section is a federal magistrate judge (or an equivalent non-specialist executive) who is smart, trained in logical analysis, but has no project controls or scheduling background. They read to decide whether something deserves a closer look — not to understand the calculation. Every finding you describe must pass this test: a reader could state it back to someone else in 30 seconds without needing to look at the report again. If it requires the report, you have written it too technical. USER: Produce the plain-language findings section of a schedule analysis report. Project name: {project_name} Versions compared: {version_a_name} (dated {status_date_a}) → {version_b_name} (dated {status_date_b}) Findings detected by the analysis engine (HIGH confidence only — MEDIUM and LOW are not included in this section): {findings_block_high_only} Aggregate manipulation score (0-100, normalized): {score} Patterns contributing to the score: {top_patterns} Produce the narrative in this structure, and only this structure: 1. What this report looked at — 2 to 3 sentences, no jargon. Example: "This analysis compares two versions of the [project] schedule issued roughly [N months/years] apart. It looks for patterns of change between the two versions that would be unusual for a typical project update and might deserve additional investigation." 2. The short answer — 2 to 4 sentences. State in plain English what the analysis found, including the count of high-confidence findings and the general nature of the pattern. Example of the style target: "The analysis found [N] high-confidence patterns of change that would be unusual for a typical schedule update. The pattern, taken together, suggests that between [date A] and [date B], the schedule was adjusted in ways that reduced the apparent amount of delay shown to readers of the schedule, even though the underlying work had not changed." 3. The top three findings — exactly three, the highest-confidence three. For each: a. A short title in plain English (no jargon). Not "Lag Laundering on FS links" — "Hidden waiting time inserted between tasks to absorb delay." b. What the evidence shows, in 4 to 5 sentences. Use specific task descriptions rather than task IDs where possible. Use calendar dates rather than "status date of period A." Use "the work planned for [month year]" rather than "task UID 1247." c. Why this would matter — 2 to 3 sentences. Connect the finding to what a project sponsor or decision-maker would care about: did it hide a delay, did it move a milestone, did it change who was on the critical path. d. The innocent explanation, if there is one — 1 to 2 sentences. Acknowledge what a reasonable scheduler might say in defense of the change, if the scheduler had a legitimate reason. e. The analyst's read — one sentence. Use the phrases "the evidence supports," "the evidence is mixed," or "the evidence is inconclusive." Never say "intentional" or "manipulative." 4. The overall picture — one paragraph. Step back from the individual findings and describe what the aggregate pattern does or does not tell us. If the findings all point in the same direction, say so. If they are scattered, say so. If they cluster in one area of the project or one time period, say so. 5. What this report cannot tell you — explicitly enumerate as a bulleted list: - This analysis does not determine intent. - This analysis reflects only the schedule files reviewed. Contract documents, emails, and project records are not part of this review. - This analysis does not substitute for testimony by a qualified expert. - This analysis's findings have confidence levels. High confidence means the evidence is strong within the schedule data; it does not mean the finding is proven beyond dispute. 6. A glossary — exactly 8 to 12 terms used in the above narrative. Each term defined in one to two plain sentences. Include at minimum: critical path, float, status date, baseline, predecessor / successor, constraint, Unique ID. Do not include terms that you did not actually use in sections 1-5. Rules for this section: - Do not use any acronym without defining it on first use. DCMA, CPM, TF, FS/SS/FF/SF — all defined in plain English on first use or replaced with a plain-English description. - Do not use formulas. - Do not cite section numbers from governing documents (PAM 200.1, NASA handbook). Those belong in the scheduler report. - Use specific calendar dates (e.g., "February 15, 2025") in preference to "period A status date." - Use calendar durations (e.g., "about four months") in preference to working-day counts. - Never refer to "the contractor" or "the owner." The data does not attribute change to a party. - Length target: keep section 3 (the three findings) between 400 and 600 words total — this is the section the reader will actually study. Other sections are supporting. Return only the narrative. Do not include headers beyond the ones the structure requires. Do not explain your reasoning. Produce the finished narrative as it will appear in the final report. |
| When to use | Called from app/prompts/pm_judge_narrative.j2 (or equivalent) whenever the PM / judge report is generated. Ships with the tool. |
| Common failure | Model produces a softened version of the scheduler report rather than a ground-up plain-language explanation. Counter with the explicit 'state back in 30 seconds without looking at the report' test and by forbidding formulas and governing-document citations. |
| Best combos | Prompt C.1 for the scheduler version; Prompt C.4 for the overall project summary that both reports share. |
| Proficiency | Advanced |

## Prompt C.3 — The DCMA metric explainer prompt

| Plan Mode | NO — Same as C.1. |
| --- | --- |
| Why it works | A DCMA metrics table with 14 rows of red/yellow/green is useless to a non-specialist and not forensically defensible for a specialist unless each metric's failure is explained with the specific UIDs and the specific formula. This prompt renders one explanation per failed metric, grounded in the skill's formula, with the triggered UIDs cited. It's called once per failed metric by the report generator. |
| Example prompt | SYSTEM: You are a forensic schedule analyst explaining a single DCMA 14-point metric failure to a mixed audience that includes the scheduler of record and an executive reviewer. Your explanation must satisfy both: technical enough that the scheduler cannot dismiss it, plain enough that the executive understands what happened and why it matters. You do not exaggerate the significance of a metric failure. A red DCMA metric is an investigative trigger, not an automatic conclusion. Some red metrics have legitimate causes; some red metrics are red because of schedule data that matters less than others. Your explanation must make that distinction clear. USER: Explain the following DCMA 14-point metric failure in exactly the structure below. Metric: {metric_name} Metric number: {metric_number} Value: {metric_value} Threshold: {metric_threshold} Status: {metric_status} (will be WARN or FAIL — skip if PASS) Formula: {metric_formula} Exclusions from denominator: {exclusions_applied} Triggered UIDs ({triggered_count} total): {triggered_uids_list} Sample of triggered tasks (up to 5, with task names and key field values): {triggered_tasks_sample} Schedule context: {project_name}, status date {status_date}, total tasks {task_count} Structure: 1. What the metric measures — one sentence in plain English. Example: "This metric measures the percentage of tasks in the schedule that have no predecessor or no successor — tasks that appear to 'dangle' from the rest of the project logic." 2. What the data shows — two to three sentences. State the value, the threshold, and the raw count. Example: "Of [denominator] tasks eligible for this check (excluding [exclusions], per DCMA-EA PAM 200.1 Section 4), [triggered_count] tasks failed the check, producing a metric value of [value]%. DCMA's threshold for a passing schedule is [threshold]%." 3. Why this matters — two to three sentences. State what this metric's failure implies about the schedule's usefulness and why a reader should care. Avoid overstatement. 4. Examples — cite 3 to 5 specific tasks from the triggered_tasks_sample, with their names and the specific field value that caused the failure. Example: "Task 'Procure long-lead valves' (Unique ID 1247) has no successor task defined. Task 'Install bulkhead fitting' (Unique ID 1589) has no predecessor task defined." 5. Possible legitimate causes — one to two sentences. Example for missing logic: "Some lack of logic can be legitimate, especially for project start and finish milestones and for external deliveries that are intentionally left unlinked. A reviewer should confirm whether the triggered tasks fit those categories before treating the metric failure as a problem." 6. Recommended review action — one sentence. Example: "The full list of triggered tasks is in the drill-down workbook, sheet 'DCMA details'. Review the list against project scope to confirm whether any of the dangling tasks are on the project's critical or near-critical paths." Rules: - No explanation of how the formula is calculated — that goes in the methodology appendix of the scheduler report. - No conclusions about intent, quality of the scheduler, or overall schedule health — this is one metric, not an assessment. - Every specific UID cited must appear in the triggered_tasks_sample provided. Length target: 180 to 280 words. Trim tighter if fewer than 3 examples are available. Return only the explanation for this one metric. No header, no metric name as a title. The calling code will handle section structure. |
| When to use | Called from the report generator once per WARN or FAIL metric. Skipped for PASS metrics (those are tabulated but not narrated). |
| Common failure | Model overstates the significance — 'this is a major finding' — or understates it — 'this is a trivial issue.' Counter via the 'do not exaggerate' system instruction and the explicit recommended-review-action framing rather than a conclusions framing. |
| Best combos | Prompt C.1 (scheduler narrative) calls this prompt once per failed metric to build the DCMA section; Prompt C.2 (PM / judge narrative) cites only the top 2 or 3 metric failures with this style. |
| Proficiency | Intermediate |

## Prompt C.4 — The driving path trace explainer prompt

| Plan Mode | NO — Same as C.1. |
| --- | --- |
| Why it works | Driving path trace output is a structured list of links — perfect for a drill-down workbook and useless as narrative. The value of a driving path is in what it tells you about why a milestone moved or a critical task became critical. This prompt converts the trace into the narrative that actually supports a finding, grounded in the SSI definition of driving slack rather than a generic 'predecessors of the critical path' framing. |
| Example prompt | SYSTEM: You are a forensic schedule analyst explaining a driving path trace. Driving path is not the same as critical path. A task on the critical path has total float near zero. A driving predecessor is a predecessor whose relationship slack is zero — meaning it is directly dictating the successor's timing. Per Structured Solutions Inc.'s guidance on driving slack, driving slack is the most accurate basis for tracing a project's critical path or any driving path. Your job is to explain, in narrative form, what the driving path of a specified target task actually is — what chain of work is directly dictating this task's timing, and what would have to change for the target task to move earlier. USER: Explain the driving path for the following target task. Target task UID: {target_uid} Target task name: {target_name} Target's current early finish: {target_ef} Target's total float: {target_tf_days} working days Driving path trace (ordered from project start to target, each row = one task on the chain): {trace_table} For each link in the chain, the trace includes: predecessor UID, predecessor name, relationship type (FS/SS/FF/SF), lag value, relationship slack value. If relationship slack = 0 for every link, the trace is clean. If any link has a non-zero relationship slack, the trace contains a gap and must be reported as incomplete. Produce the explanation in this structure: 1. One-sentence headline. State what task the trace targets and how many links the chain contains. Example: "The driving path to [target_name] contains [N] linked tasks stretching back to [first task in chain]." 2. A narrative of the chain. Walk the reader through the key segments (3-5 chunks, not 20) of the chain. For each chunk, state what work is happening in plain English and how long it takes. Example: "The chain begins with [first task] in [approximate date range]. That task's completion releases [next N tasks in the chunk], which together take about [duration] and end with [last task of chunk]. From there, [next chunk]..." 3. What would have to change for the target task to move earlier. State the driving predecessors whose reduction in duration or earlier finish would most directly pull the target forward. Example: "The single link with the largest influence on [target_name]'s timing is [driving predecessor name], with an early finish of [date]. Any reduction in that task's duration or an earlier start for that task would directly advance [target_name]. Tasks further back in the chain are also driving, but their impact on [target_name] is mediated through the intermediate tasks." 4. Any non-driving predecessors flagged — if the target task has predecessors that do NOT appear in the driving chain (because their relationship slack is > 0), state briefly that those predecessors have slack and are not currently dictating the target's timing. This is useful context for a reader who expected to see those predecessors in the chain. 5. Caveats — one to two sentences. State what the trace does and does not tell you. Example: "This trace reflects the schedule's logic as calculated. It does not account for physical, resource, or contractual reasons a successor task could not actually start earlier even if its driving predecessor moved." Rules: - Acronyms: CPM, TF, FS/SS/FF/SF defined on first use. - Dates: calendar dates when available, working days otherwise. - Task names before UIDs. UIDs in parentheses after the first mention of a task. - Do not claim the chain is the only way to advance the target. Resource or scope changes can bypass logic constraints in ways the schedule does not reflect. Length target: 200-350 words depending on chain length. |
| When to use | Called from the report generator when a finding requires a driving path trace as supporting evidence. Typically invoked for the top HIGH-confidence findings whose evidence includes a trace. |
| Common failure | Model confuses driving path and critical path, producing a trace explanation that says 'these tasks are all critical' when in fact some of them are on the driving path but not on the critical path. Counter via the explicit SSI definition in the system prompt. |
| Best combos | Prompt C.1 (scheduler narrative) invokes this when a finding's evidence mentions a driving path. |
| Proficiency | Advanced |

## Prompt C.5 — The Claude-API-vs-Ollama toggle handler

| Plan Mode | NO — Decision rubric for the AI router code, not a pasteable prompt. Plan mode is not applicable — you implement the rubric directly. |
| --- | --- |
| Why it works | The CUI gate — when to use the local Ollama model vs. when to use the Claude API — cannot be a silent defaulting decision. If the tool silently routes CUI data to Claude API because Ollama is slow or unavailable, that's a compliance incident. This prompt lives in the toggle-handler code path and is NOT sent to the LLM — it's the decision rubric the Python code implements. Including it in this document so the runtime behavior is explicit, auditable, and reviewable. |
| Example prompt | # This is not an LLM prompt. This is the decision rubric the Python toggle handler # in app/ai_router.py must implement. The implementation must match this rubric # exactly; any divergence is a CUI compliance incident. Inputs at analysis time: - user_toggle: either "ollama" (default) or "claude_api" - schedule_classification: either "CUI" (default, applied when unknown) or "UNCLASSIFIED" (requires explicit user opt-in per analysis, with a checkbox the user must affirmatively select) - ollama_health: "available" or "unavailable" - claude_api_health: "available" or "unavailable" Routing rules (evaluated in order): Rule 1 — CUI data NEVER leaves the machine. If schedule_classification == "CUI": IF user_toggle == "claude_api": refuse the request with the error message: "This schedule is marked CUI. Claude API routing is not permitted for CUI data. Switch to Ollama (local) or mark the schedule unclassified explicitly via the analysis-configuration screen if the schedule is in fact unclassified." ELSE: # ollama path IF ollama_health == "unavailable": refuse the request with the error message: "Ollama is required for CUI analysis but is not currently responding. Please start the Ollama service and retry. Analysis did NOT fall back to Claude API because this schedule is CUI." ELSE: route to ollama. Rule 2 — Unclassified data, toggle = ollama. If schedule_classification == "UNCLASSIFIED" and user_toggle == "ollama": IF ollama_health == "available": route to ollama. ELSE: refuse the request (do not silently fall back to Claude API — the user toggle is a stated preference). Error: "Ollama is unavailable. You may switch to Claude API for this unclassified analysis, but the tool will not do so automatically." Rule 3 — Unclassified data, toggle = claude_api. If schedule_classification == "UNCLASSIFIED" and user_toggle == "claude_api": IF claude_api_health == "available": route to claude_api. Log the routing decision with timestamp, schedule identifier hash (not name or contents), and user identity to logs/ai_routing_YYYY-MM.log. ELSE: refuse the request. Error: "Claude API is unavailable. Switch to Ollama or try again later." Rule 4 — No silent fallback. Under no condition does the toggle handler route to the non-toggled endpoint without a UI-level explicit user confirmation for this specific analysis. The toggle is a preference that the user owns, not a hint the router can override. Logging rules for the routing decision: - Never log schedule file contents, task names, UIDs, or any parsed data. - Do log: user identity, timestamp, schedule classification, toggle value, routing decision, ollama_health, claude_api_health. - Log file is rotated monthly, retained 12 months. Test assertions required (in tests/test_ai_router.py): - CUI + claude_api toggle → refusal. - CUI + ollama toggle + ollama unavailable → refusal with no attempt to use claude_api. - Unclassified + ollama toggle + ollama unavailable → refusal (no silent fallback). - Unclassified + claude_api toggle + claude_api unavailable → refusal. - No test permutation routes to claude_api without user_toggle == "claude_api" and schedule_classification == "UNCLASSIFIED". |
| When to use | Implemented in app/ai_router.py. The code enforces this rubric at every call site that would invoke an LLM. |
| Common failure | Developer implements a 'fallback to available backend' convenience that silently routes CUI data to Claude API when Ollama is slow. This is the single worst failure mode in the whole tool. Counter by the explicit no-silent-fallback rule and by the test assertions that specifically prohibit it. |
| Best combos | Prompt B.1 through B.7 all call into the AI router via this rubric; Prompt A.4 (watchdog) flags any attempt to bypass this rubric as a BLOCKER violation. |
| Proficiency | Advanced |

# Combo Recipes

These are the exact stacks for common build tasks — how to chain the prompts in this guide together for specific outcomes.

## Recipe 1 — Full build from zero to first working tool

The end-to-end sequence. Each row is one Claude Code session. Do not combine. The session isolation is the point.

| Session | Prompt | Purpose |
| --- | --- | --- |
| 0a | Prompt 0.0.1 | Pre-build repository audit — read-only inventory and classification (added Ed. 1.1) |
| 0b | Prompt 0.0.2 | Archive prior-build artifacts into dated archive folder with git mv (added Ed. 1.1) |
| 1 | Prompt 0.1 | Scaffold the skill library (8 empty skills, committed) — runs after housekeeping is complete |
| 1a | Prompt 0.5 | Gate CI pytest on tests/ existing — prevents red CI from hiding real regressions during rebuild window (added Ed. 1.3) |
| 2-9 | Prompt 0.2 + 0.3 | Populate one skill per session, audit immediately after each |
| 10 | Prompt 0.4 | Cross-skill consistency check, apply edits |
| 11 | Prompt A.1 | Master orchestration plan committed to docs/BUILD-PLAN.md |
| 12 | Prompt A.2 for Phase 1 | Repo audit + harvest phase prompts committed |
| 13 | Prompt B series, Phase 1 work | Specialist session building audit outputs; Watchdog A.4 runs concurrently |
| 14 | Prompt A.3 Council on Phase 1 | Three-reviewer audit |
| 15 | Prompt A.5 handoff to Phase 2 | Handoff artifact committed |
| 16-90+ | Repeat A.2 → B.N → A.4 → A.3 → A.5 for phases 2-14 | One session per specialist phase step |
| Final | Prompt B.7 + integration test from Phase 13 | Launcher works from desktop shortcut; synthetic schedule produces both reports |

## Recipe 2 — Debug session when a phase fails council review

The loop that turns a REJECT or REVISE verdict into a clean acceptance.

- Council review returns REVISE with a specific edit list. Coordinator reads the list and the original Prompt B.X used in the phase.

- Coordinator identifies which specialist prompt needs revision (usually ambiguity in a requirement that let the specialist make a wrong choice).

- Coordinator rewrites Prompt B.X with the specific clarification. The edit is localized, not a rewrite.

- Specialist session runs the revised prompt in a fresh context. Prior attempt's branch is archived, not overwritten.

- Watchdog (Prompt A.4) runs against the new specialist branch.

- Council review re-runs (Prompt A.3).

- If accepted, handoff (Prompt A.5) commits and advances to next phase. If rejected again, escalate to you for the decision on whether the requirement itself is wrong.

## Recipe 3 — Add a new manipulation pattern after initial build

When you discover an eleventh manipulation pattern post-launch. The skill library is where it lands first — NOT the forensics module directly.

- Update the forensic-manipulation-patterns skill with the new pattern's definition, detection algorithm, evidence requirements, and defense plausibility. Validate with Prompt 0.3.

- Run Prompt 0.4 to confirm the new pattern doesn't contradict driving-slack-and-paths or dcma-14-point-assessment.

- Open a Prompt B.5 specialist session that adds one detector function (detect_NEW_PATTERN_NAME) and its scoring entry. Do NOT rewrite the other nine detectors.

- Council review (Prompt A.3) with a lens on: does this new pattern double-count evidence already captured by an existing pattern? If yes, adjust scoring ceiling.

- Update the runtime prompts (C.1, C.2) to include the new pattern name in their expected pattern list. Usually no prompt text changes are needed if the naming is consistent.

# Master Cheat Sheet — Problem → Prompt Index

One table. If your current problem shape matches the left column, run the prompts in the right column, in order.

| Problem shape | Prompt(s) to run, in order |
| --- | --- |
| You're starting the rebuild and the repo already has prior-build content in it (app/, ollama/, tests/, etc.) | 0.0.1 → (human review) → 0.0.2 → 0.1 |
| You're starting the rebuild from a genuinely empty repo | 0.1 → 0.2 → 0.3 → 0.4 → A.1 |
| You ran 0.1 before housekeeping and now .claude/skills/ sits alongside an old app/ tree | Stop. Revert 0.1's commit. Run 0.0.1 → 0.0.2 → re-run 0.1 cleanly. |
| A Claude Code session is writing code without context on DCMA / NASA / driving slack | Stop. Fix the skill library first: 0.1-0.4. Then resume. |
| A phase feels like scope creep is starting | Invoke A.4 (watchdog). If BLOCKER found, revert and revise A.2. |
| A module was built but you don't trust the output | A.3 (council) with three reviewers on different lenses. |
| You need to hand off from phase N to phase N+1 | A.5 (handoff artifact) |
| The parser returns wrong values | B.1 re-run after checking that the mpp-parsing-com-automation skill addresses the specific gotcha |
| Critical path math is off | B.2 re-run; check driving-slack-and-paths skill |
| Cross-version comparison is producing phantom task moves | Confirm B.3 is using UniqueID only; re-run the UID-rename test |
| DCMA score is 100/100 always (the prior-build failure) | B.4 re-run with normalized scoring and per-UID dedup assertions. See also the Schedule_Forensics_Lessons_Learned.md prior-build failure mode. |
| Manipulation findings don't hold up in review | B.5 council review with a Daubert-compliance lens |
| Reports bleed voice between scheduler and PM audiences | B.6 council review with separate voice-audit passes per report |
| Launcher works manually, fails from shortcut | B.7 with the cmd.exe /k pattern |
| Runtime narrative sounds like an expert report when it should sound like a judge briefing | Swap C.1 for C.2; verify the 'state back in 30 seconds' rule |
| Ollama was unavailable and the tool sent CUI data to Claude API | STOP USING THE TOOL. This is a compliance incident. C.5 rule 4 was violated — investigate the code path; run the test assertions. |
| A skill file contradicts another skill file | 0.4 |
| CI is red on every PR because pytest can't find tests/ after the archive | 0.5 (one-time fix that heals itself when Phase 2 restores tests/) |
| Claude Code wants to reuse a stale feature branch for new work | Refuse. One branch per phase. Check out main, branch fresh as claude/<phase-id>-YYYY-MM-DD, cherry-pick any committed work onto it if needed. |
| Claude Code's Plan Mode produced a 500-line plan that looks like the implementation already | Interrupt with 'shorter plan, execute'. A good plan is skimmable in 30 seconds. If it runs longer, the plan has overrun into the implementation and you are about to lose context to a draft that never commits. |
| You suspect drift in the current chat session | Load the latest Schedule_Forensics_Prompt_Engineering_Reference_Guide and ask Claude to reconcile its current proposal against the committed plan |

Final reminder: This guide teaches prompts. Prompts are the surface. The value is in what the prompts commit you to: phase-gated discipline, UID-not-TaskID matching, COM automation over MPXJ, normalized manipulation scoring, separate reports for separate audiences, CUI never leaves the machine. The prompts are how you force Claude Code to respect those commitments session after session. If any future version of yourself — or any future instance of Claude — tries to shortcut any of those commitments to save a session, that's when you reread this document.